## Cover Page
SIT Non-Functional Test Scenarios - Theme 2
Document owner | Document number | Version
SI Test Team | MHHS-DEL3659 | 0.1
Status: | Date | Classification
Draft | 2025-06-16 | Public

## Change Control
Change Record
Date | Author | Version | Change Detail
2025-04-16 | SI NFT Team | 0.1 | First draft for review by SRO
Document Approval
Reviewer/Approver | Role
SI Test Team | Internal review
SRO Design Team | Approval ahead of industry review
Code Bodies | Approval ahead of industry review
NFTWG | Recommendation to TMAG
SITAG | Approval
References
Reference | Documents | Publisher | Version | Additional Information
Design Interface | MHHSP-DES138-Interface Catalogue |  | 5.7.1
Requirements | MHHS-E2E002 Requirements |  | 3.1
| MHHS-DEL2128 NFR Categorisation |  | 2
MHHS-DEL2324 Initial BAU Volume Model
| MHHS-DEL396 MHHS-DIP002 Functional & Non-Functional Requirements |  | 2.2
MHHSP_OPC001_Operational_Choreography
PIT Guidance | MHHS-DEL852 - Pre-Integration Test Guidance |  | 2.5
NFT | MHHS-DEL2437 Non-Functional Test Policy |  | 0.3
| MHHS-DEL2127 SIT Non-Functional Test Approach & Plan |  | 0.5
Terminology
Term | Description
For terminology, see programme glossary on the MHHS portal

## Theme 2 Daily Allocation
Key
20 stated in runbook, however, if possible, all MPANs as estimates
blank, notifcations are being set-up for day 2 processing
blank, these test cases will process their respective MPAN notification from the previous day
MPAN Allocation to Test Cases, Run book for paired Cohorts
Day1
[9 empty] | Cohorts - Re-usable Data | [10 empty] | COS - Data Loss
[9 empty] | AJ |  | AGJ - UMSDS |  |  | BF |  | GH |  | CE |  | COS Cases |  | Cohort Direction
Process Under Test | Test Scenario Ref | Test Case Ref | Start Role/IF | Meter Group | Relationship | Measurement Class | Import/Export | MPAN Cat | A | J | A | G | J | B | F | G | H | C | E | SOUT | ETCL
IF-021 | SITNFT-T2-020 | SITNFT-T2-020-010-SMART | SDS IF-021 | Smart | Single | All available | All available | All available | 20 | 20 |  |  |  | 20 | 20 | 20 | 20 | 20 | 20
|  | SITNFT-T2-020-020-SMART_IF014 | SDS F-021 | Smart | Single |  |  |  | 20 | 20 |  |  |  | 20 | 20 | 20 | 20 | 20 | 20
|  | SITNFT-T2-020-030-TRAD | SDS IF-021 | Traditional | Single | All available | All available | All available | 20 | 20 |  |  |  | 20 | 20 | 20 | 20 | 20 | 20
|  | SITNFT-T2-020-040-ADV | ADS F-021 | Advanced | Single | All available | All available | All available | 20 | 20 |  |  |  | 20 | 20 | 20 | 20 | 20 | 20
|  | SITNFT-T2-020-050-UM | UMSC F-021 | Unmetered | Single | All available | All available | All available | 20 | 20 |  |  |  | 20 | 20 | 20 | 20 | 20 | 20
n/a | SITNFT-T2-030 | SITNFT-T2-030-010-LSS-Sched |  | n/a
Notification & Appointments | SITNFT-T2-040 (COSupplier_Notification_Processing) | SITNFT-T2-040-010-Smart | Regs IF-002 | Smart | Single | NHH | I | C3-M-04_SOUT_1 | [11 empty] | 40 | 40 | J-->A
| SITNFT-T2-050 (COA_Notification_Processing) | SITNFT-T2-050-010-Smart | Supplier IF-031 | Smart | Single | any | I |  | A: 20; B: 20; G: 20; C: 20
|  | SITNFT-T2-050-020-Adv | Supplier IF-031 | Advanced | Single | any | I |  | A: 20; B: 20; G: 20; C: 20
|  | SITNFT-T2-050-030-Trad | Supplier IF-031 | Traditional | Single | any | I |  | A: 20; B: 20; G: 20; C: 20
|  | SITNFT-T2-050-040-Adv | Supplier IF-031 | Advanced | Import/Export | any | I/E |  | A: 20; B: 20; G: 20; C: 20
|  | SITNFT-T2-050-050-Trad | Supplier IF-031 | Traditional | Related | any | I |  | A: 20; B: 20; G: 20; C: 20
|  | SITNFT-T2-050-060-UM | Supplier IF-031 | Unmetered | Single | any | I |  | A: 20
Appointment Processing | SITNFT-T2-060 (COSUpplier_Processing) | SITNFT-T2-060-010-Smart | Regs IF-037 | Smart | Single
| SITNFT-T2-070 (COA_Processing) | SITNFT-T2-070-010-Smart | Regs IF-037 | Smart | Single
|  | SITNFT-T2-070-020-Adv | Regs IF-037 | Advanced | Single
|  | SITNFT-T2-070-030-Trad | Regs IF-037 | Traditional | Single
|  | SITNFT-T2-070-040-Adv | Regs IF-037 | Advanced | Import/Export
|  | SITNFT-T2-070-050-Trad | Regs IF-037 | Traditional | Related
|  | SITNFT-T2-070-060-UM | Regs IF-037 | Unmetered | Single
Day2
[9 empty] | A: Cohorts - Re-usable Data | COS - Data Loss
[9 empty] | A: AJ; A: AGJ - UMSDS; B: BF; G: GH; C: CE | COS Cases |  | Cohort Direction
Process Under Test | Test Scenario Ref | Test Case Ref | Start Role/IF | Meter Group | Relationship | Measurement Class | Import/Export | MPAN Cat | A | J | A | G | J | B | F | G | H | C | E | SOUT | ETCL
IF-021 | SITNFT-T2-020 | SITNFT-T2-020-010-SMART | SDS IF-021 | Smart | Single | All available | All available | All available | 20 | 20 |  |  |  | 20 | 20 | 20 | 20 | 20 | 20
|  | SITNFT-T2-020-020-SMART_IF014 | SDS F-021 | Smart | Single |  |  |  | 20 | 20 |  |  |  | 20 | 20 | 20 | 20 | 20 | 20
|  | SITNFT-T2-020-030-TRAD | SDS IF-021 | Traditional | Single | All available | All available | All available | 20 | 20 |  |  |  | 20 | 20 | 20 | 20 | 20 | 20
|  | SITNFT-T2-020-040-ADV | ADS F-021 | Advanced | Single | All available | All available | All available | 20 | 20 |  |  |  | 20 | 20 | 20 | 20 | 20 | 20
|  | SITNFT-T2-020-050-UM | UMSC F-021 | Unmetered | Single | All available | All available | All available | 20 | 20 |  |  |  | 20 | 20 | 20 | 20 | 20 | 20
n/a | SITNFT-T2-030 | SITNFT-T2-030-010-LSS-Sched |  | n/a
Notification & Appointments | SITNFT-T2-040 (COSupplier_Notification_Processing) | SITNFT-T2-040-010-Smart | Regs IF-002 | Smart | Single | NHH | I | C3-M-04_SOUT_1 | [11 empty] | 40 | 40 | B-->F
| SITNFT-T2-050 (COA_Notification_Processing) | SITNFT-T2-050-010-Smart | Supplier IF-031 | Smart | Single | any | I |  | J: 20; F: 20; H: 20; E: 20
|  | SITNFT-T2-050-020-Adv | Supplier IF-031 | Advanced | Single | any | I |  | J: 20; F: 20; H: 20; E: 20
|  | SITNFT-T2-050-030-Trad | Supplier IF-031 | Traditional | Single | any | I |  | J: 20; F: 20; H: 20; E: 20
|  | SITNFT-T2-050-040-Adv | Supplier IF-031 | Advanced | Import/Export | any | I/E |  | J: 20; F: 20; H: 20; E: 20
|  | SITNFT-T2-050-050-Trad | Supplier IF-031 | Traditional | Related | any | I |  | J: 20; F: 20; H: 20; E: 20
|  | SITNFT-T2-050-060-UM | Supplier IF-031 | Unmetered | Single | any | I |  | G: 20
Appointment Processing | SITNFT-T2-060 (COSUpplier_Processing) | SITNFT-T2-060-010-Smart | Regs IF-037 | Smart | Single
| SITNFT-T2-070 (COA_Processing) | SITNFT-T2-070-010-Smart | Regs IF-037 | Smart | Single
|  | SITNFT-T2-070-020-Adv | Regs IF-037 | Advanced | Single
|  | SITNFT-T2-070-030-Trad | Regs IF-037 | Traditional | Single
|  | SITNFT-T2-070-040-Adv | Regs IF-037 | Advanced | Import/Export
|  | SITNFT-T2-070-050-Trad | Regs IF-037 | Traditional | Related
|  | SITNFT-T2-070-060-UM | Regs IF-037 | Unmetered | Single
Day3
[9 empty] | A: Cohorts - Re-usable Data | COS - Data Loss
[9 empty] | A: AJ; A: AGJ - UMSDS; B: BF; G: GH; C: CE | COS Cases |  | Cohort Direction
Process Under Test | Test Scenario Ref | Test Case Ref | Start Role/IF | Meter Group | Relationship | Measurement Class | Import/Export | MPAN Cat | A | J | A | G | J | B | F | G | H | C | E | SOUT | ETCL
IF-021 | SITNFT-T2-020 | SITNFT-T2-020-010-SMART | SDS IF-021 | Smart | Single | All available | All available | All available | 20 | 20 |  |  |  | 20 | 20 | 20 | 20 | 20 | 20
|  | SITNFT-T2-020-020-SMART_IF014 | SDS F-021 | Smart | Single |  |  |  | 20 | 20 |  |  |  | 20 | 20 | 20 | 20 | 20 | 20
|  | SITNFT-T2-020-030-TRAD | SDS IF-021 | Traditional | Single | All available | All available | All available | 20 | 20 |  |  |  | 20 | 20 | 20 | 20 | 20 | 20
|  | SITNFT-T2-020-040-ADV | ADS F-021 | Advanced | Single | All available | All available | All available | 20 | 20 |  |  |  | 20 | 20 | 20 | 20 | 20 | 20
|  | SITNFT-T2-020-050-UM | UMSC F-021 | Unmetered | Single | All available | All available | All available | 20 | 20 |  |  |  | 20 | 20 | 20 | 20 | 20 | 20
n/a | SITNFT-T2-030 | SITNFT-T2-030-010-LSS-Sched |  | n/a
Notification & Appointments | SITNFT-T2-040 (COSupplier_Notification_Processing) | SITNFT-T2-040-010-Smart | Regs IF-002 | Smart | Single | NHH | I | C3-M-04_SOUT_1 | [11 empty] | 40 | 40 | G-->H
| SITNFT-T2-050 (COA_Notification_Processing) | SITNFT-T2-050-010-Smart | Supplier IF-031 | Smart | Single | any | I |  | A: 20; B: 20; G: 20; C: 20
|  | SITNFT-T2-050-020-Adv | Supplier IF-031 | Advanced | Single | any | I |  | A: 20; B: 20; G: 20; C: 20
|  | SITNFT-T2-050-030-Trad | Supplier IF-031 | Traditional | Single | any | I |  | A: 20; B: 20; G: 20; C: 20
|  | SITNFT-T2-050-040-Adv | Supplier IF-031 | Advanced | Import/Export | any | I/E |  | A: 20; B: 20; G: 20; C: 20
|  | SITNFT-T2-050-050-Trad | Supplier IF-031 | Traditional | Related | any | I |  | A: 20; B: 20; G: 20; C: 20
|  | SITNFT-T2-050-060-UM | Supplier IF-031 | Unmetered | Single | any | I |  | J: 20
Appointment Processing | SITNFT-T2-060 (COSUpplier_Processing) | SITNFT-T2-060-010-Smart | Regs IF-037 | Smart | Single
| SITNFT-T2-070 (COA_Processing) | SITNFT-T2-070-010-Smart | Regs IF-037 | Smart | Single
|  | SITNFT-T2-070-020-Adv | Regs IF-037 | Advanced | Single
|  | SITNFT-T2-070-030-Trad | Regs IF-037 | Traditional | Single
|  | SITNFT-T2-070-040-Adv | Regs IF-037 | Advanced | Import/Export
|  | SITNFT-T2-070-050-Trad | Regs IF-037 | Traditional | Related
|  | SITNFT-T2-070-060-UM | Regs IF-037 | Unmetered | Single
Day4
[9 empty] | A: Cohorts - Re-usable Data | COS - Data Loss
[9 empty] | A: AJ; A: AGJ - UMSDS; B: BF; G: GH; C: CE | COS Cases |  | Cohort Direction
Process Under Test | Test Scenario Ref | Test Case Ref | Start Role/IF | Meter Group | Relationship | Measurement Class | Import/Export | MPAN Cat | A | J | A | G | J | B | F | G | H | C | E | SOUT | ETCL
IF-021 | SITNFT-T2-020 | SITNFT-T2-020-010-SMART | SDS IF-021 | Smart | Single | All available | All available | All available | 20 | 20 |  |  |  | 20 | 20 | 20 | 20 | 20 | 20
|  | SITNFT-T2-020-020-SMART_IF014 | SDS F-021 | Smart | Single |  |  |  | 20 | 20 |  |  |  | 20 | 20 | 20 | 20 | 20 | 20
|  | SITNFT-T2-020-030-TRAD | SDS IF-021 | Traditional | Single | All available | All available | All available | 20 | 20 |  |  |  | 20 | 20 | 20 | 20 | 20 | 20
|  | SITNFT-T2-020-040-ADV | ADS F-021 | Advanced | Single | All available | All available | All available | 20 | 20 |  |  |  | 20 | 20 | 20 | 20 | 20 | 20
|  | SITNFT-T2-020-050-UM | UMSC F-021 | Unmetered | Single | All available | All available | All available | 20 | 20 |  |  |  | 20 | 20 | 20 | 20 | 20 | 20
n/a | SITNFT-T2-030 | SITNFT-T2-030-010-LSS-Sched |  | n/a
Notification & Appointments | SITNFT-T2-040 (COSupplier_Notification_Processing) | SITNFT-T2-040-010-Smart | Regs IF-002 | Smart | Single | NHH | I | C3-M-04_SOUT_1 | [11 empty] | 40 | 40 | C-->E
| SITNFT-T2-050 (COA_Notification_Processing) | SITNFT-T2-050-010-Smart | Supplier IF-031 | Smart | Single | any | I |  | J: 20; F: 20; H: 20; E: 20
|  | SITNFT-T2-050-020-Adv | Supplier IF-031 | Advanced | Single | any | I |  | J: 20; F: 20; H: 20; E: 20
|  | SITNFT-T2-050-030-Trad | Supplier IF-031 | Traditional | Single | any | I |  | J: 20; F: 20; H: 20; E: 20
|  | SITNFT-T2-050-040-Adv | Supplier IF-031 | Advanced | Import/Export | any | I/E |  | J: 20; F: 20; H: 20; E: 20
|  | SITNFT-T2-050-050-Trad | Supplier IF-031 | Traditional | Related | any | I |  | J: 20; F: 20; H: 20; E: 20
|  | SITNFT-T2-050-060-UM | Supplier IF-031 | Unmetered | Single | any | I |  | A: 20
Appointment Processing | SITNFT-T2-060 (COSUpplier_Processing) | SITNFT-T2-060-010-Smart | Regs IF-037 | Smart | Single
| SITNFT-T2-070 (COA_Processing) | SITNFT-T2-070-010-Smart | Regs IF-037 | Smart | Single
|  | SITNFT-T2-070-020-Adv | Regs IF-037 | Advanced | Single
|  | SITNFT-T2-070-030-Trad | Regs IF-037 | Traditional | Single
|  | SITNFT-T2-070-040-Adv | Regs IF-037 | Advanced | Import/Export
|  | SITNFT-T2-070-050-Trad | Regs IF-037 | Traditional | Related
|  | SITNFT-T2-070-060-UM | Regs IF-037 | Unmetered | Single