## Sheet1
Organisation: | Various
Constituency: | Various |  |  | MHHS-DEL2695 Consolidated Comments Log (This Artefact)
Date: | 2024-05-30 |  |  | Comments on artefact 'MHHS-DEL2531 SIT Non-Functional Test Scenarios Theme1 v0.1'
Anonymised:
Write Yes to indicate if you'd like your responses anonymised in the Consolidated Comments Log
| Reviewer to Complete | [5 empty] | Programme to complete once consultation window has closed.
Ref | Reviewer | Theme (select from dropdown) | Filename (enter name of the file reviewed) | Tab (enter the name of the tab) | Step No. | Comment | Accept/Reject or Action | Response | Status
1 | Elexon | NFT Theme 1 | SIT Non-Functional Test Scenarios - Theme 1 | SITNFT-T1-010 Overview |  | The test mentions LSS as the main target of the tests, but I didn't see any specific steps to trigger LSS in SITNFT-T1-010 or SITNFT-T1-010. Suggest adding the steps for clarity | Accept | LSS as a target for consumption data, alongside a supplier stub is the main driver for this set of tests, given the focus of this test is the egress of PUB-021's back out of DIP we are only wanting to see evidence of these landing in LSS and Supplier, no further processing | Closed
2 | Elexon | NFT Theme 1 | SIT Non-Functional Test Scenarios - Theme 1 |  |  | Collective Feedback : 1. On tab NFT Theme 1 Test Scenarios – why have 3 iterations? 2. Can we confirm the required throughput rather than duplicating tests? 3. On Tab SITNFT-T1-010 Overview – what is the relevance of Boundaries? If we run LSS we need more than IF-021 4. On Tab SITNFT-T1-010 Consumption and SITNFT-T1-020 Consumption Calendar Check – How do we do the Calendar check – is this not functional? Data Generator Requirements – What stubs are being referred to? | Accept | 1. Standard delivery practice, we would want to see a level of stability in the results and so would need multiple runs carried out, if the 2nd run is similar to run#1, then we would be happy with 2 runs minimum 2. The current througput is stated, this is what DIP and Helix parties are already testing to. In terms of IF-021 rates from DCC, this is still an open risk with the programme. 3. Accepted, and amended 4. We have taken the functional format for test cases, please ignore the calander field, it becomes more in scope for theme 2 onwards | Closed
3 | Elexon | NFT Theme 1 | SIT Non-Functional Test Scenarios - Theme 1 |  |  | Collective Feedback : On Sheet “NFT Theme 1 Test Scenarios” , “Subject of Test” column contains “VAS;MDS;LSS;ISD” but in the test case it is mentioned only “LSS”. | Accept | This was overlooked as the approach was changed to become more DIP specific, amended. | Closed
4 | Elexon | NFT Theme 1 | SIT Non-Functional Test Scenarios - Theme 1 |  |  | Does the scope of testing is to verify the files are received at Helix(which means at DAH) or to trigger a run at LSS, (if yes, when this should be run) and check at LSS that ingestion successful? | Accept | The focus of the test is the egress of PUB-021 from DIP, we purely need to confirm the message count/rates during execution, no firther processing would be required of these | Closed
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372