## Schedule
SIT Operations Theme 3 Batch 1 | Test Case ID | Role Supporting | 2024-02-03 | 2024-02-04 | 2024-02-05 | 2024-02-06 | 2024-02-07 | 2024-02-08 | 2024-02-09 | 2024-02-10 | 2024-02-11 | 2024-02-12 | 2024-02-13 | 2024-02-14 | 2024-02-15 | 2024-02-16 | 2024-02-17 | 2024-02-18 | 2024-02-19 | 2024-02-20 | 2024-02-21 | 2024-02-22 | 2024-02-23 | 2024-02-24 | 2024-02-25 | 2024-02-26 | 2024-02-27 | 2024-02-28 | 2024-03-01 | 2024-03-02 | Comments
MHHS-DEL3194 SITOPS SM01 - Incident Management Major Incident | SIT-OPS SM01 TC01 DIP | SDS/IMSERV DIP Technical Resolver Elexon Service Management | [28 empty] | SM01Test Case have the most handoffs between teams but 3 days should sufficient. |  | Assumptions/Dependencies (Internal Only): All users are registered and have access to Service Management. At least 1 resource available for Highlighted date SM Distribution and Comms List and Groups are ready to test from 03/02/25. Day Highlighted does not represent 8hrs of effort. Defect Retests may delay planned Execution dates for Test Cases where they are due to start that day. More Complex Scen tested first - More time to resolve issues/queries relating to process. Elexon Ser Man may be the bottle neck as all tests involve them, so have restricted how many per day they can do. | bar: 2024-02-03 to 2024-02-05
| SIT-OPS SM01 TC02 DIP (Ser) | DIP SP DIP Technical Resolver Elexon Service Management | bar: 2024-02-03 to 2024-02-05
| SIT-OPS SM01 TC03 DIP (Sec) | DIP SP DIP Technical Resolver Elexon Service Management | bar: 2024-02-03 to 2024-02-05
| SIT-OPS SM01 TC07 VAS (CR) | Supplier/EON Next Elexon Service Management VAS Tech Resolver Elexon Change Management | bar: 2024-02-05 to 2024-02-07
| SIT-OPS SM01 TC08 MDS | LDSO/BUUK MDS Tech Resolver Elexon Service Management | bar: 2024-02-06 to 2024-02-07; 2024-02-10
| SIT-OPS SM01 TC09 LSS | ADS/OCTOPUS-Kraken Elexon Service Management LSS Technical Resolvers | bar: 2024-02-06 to 2024-02-07; 2024-02-10
| SIT-OPS SM01 TC10 ISD | LDSO SSEN Elexon Service Management ISDTechnical Resolvers | bar: 2024-02-11 to 2024-02-13
| SIT-OPS SM01 TC11 ISD | Supplier BG (ENSEK) Elexon Service Management ISD Technical Resolvers | bar: 2024-02-11 to 2024-02-13
| SIT-OPS SM01 TC12 DAH | Elexon DAH team Elexon Service Management DAH Technical Resolvers | bar: 2024-02-11 to 2024-02-13
MHHS-DEL3195 SITOPS SM02 - Incident Management (normal conditions) | SIT-OPS SM02 TC03 DIP (Reg) | Supplier/ Octopus/Kracken Elexon Service Management | bar: 2024-02-20
MHHS-DEL3196 SITOPS SM03 - Change Management Request raised - normal | SIT-OPS SM03 TC01 DIP | DIP SP Elexon Service Management Elexon Change Mananagement | bar: 2024-02-14; 2024-02-17
| SIT-OPS SM03 TC02 DCC | DCC Elexon Service Management | bar: 2024-02-14; 2024-02-17
| SIT-OPS SM03 TC03 INT | Internal Elexon Team Elexon Change Management | bar: 2024-02-14; 2024-02-17
| SIT-OPS SM03 TC04 MDS | MDS SP Elexon Service Management Elexon Change Management | bar: 2024-02-14; 2024-02-17
MHHS-DEL3197 SITOPS SM04 - Change Request raised - Emergency | SIT-OPS SM04 TC01 LSS | LSS SP Elexon Service Management Elexon Change Management | bar: 2024-02-18 to 2024-02-19
| SIT-OPS SM04 TC02 DIP | DIP SP Elexon Service Management Elexon Change Management | bar: 2024-02-18 to 2024-02-19
MHHS-DEL3198 SITOPS SM06 - Request Fulfillment Service (Disable & Add) | SIT-OPS SM06 TC01 DIS | Any Service User/ PDA Elexon Request Management | bar: 2024-02-19
| SIT-OPS SM06 TC02 ADD | Any Service User/PDA Elexon Request Management | bar: 2024-02-19
MHHS-DEL3199 SITOPS SM07 - Knowledge Management | SIT-OPS SM07 TC01 SER | Any Service User/Utilita Elexon Service Management. | [28 empty] | There will need to be existing content on Day 1 of test to search | bar: 2024-02-20
| SIT-OPS SM07 TC02 CRE | Any Service User/Utilita Elexon Knowledge Management | bar: 2024-02-20
MHHS-DEL3200 SITOPS SM08 - Service Management Reporting | SIT-OPS SM08 TC01 ADHOC | Any Service User/E.ON UK Energy Services/Wheatley Elexon Service Management. | bar: 2024-02-24
| SIT-OPS SM08 TC02 SCHED | Any Service User/E.ON UK Energy Services/Wheatley Elexon Service Management | [28 empty] | Sched Report should run every day and values reports return should change by the day. | Types of Reprting - (Incidents raised, incidents closed, SLA, Incident assign by group etc). Results should be restricted ot organisation running report. | bar: 2024-02-10 to 2024-02-14; 2024-02-17 to 2024-02-21; 2024-02-24 to 2024-02-28
MHHS-DEL3201 SITOPS SM09 - Service users register and able to access Elexon SM | SIT-OPS SM09 TC01 REG | Steve Evans as MHHSP | [28 empty] | Need PP who hasnt regsitered for SM access . If no one available can use our own email address as no validations are done (Just domain verification). | bar: 2024-02-03
MHHS-DEL3202 SITOPS SM10 - Service Level Management | SIT-OPS SM10 TC01 SLA | Any Service User/EON Next | bar: 2024-02-21; 2024-02-24
MHHS-DEL3203 SITOPS SM11 - Service Catalogue | SIT-OPS SM11 TC01 CAT | Any Service User/BUUK Elexon Service Management. | bar: 2024-02-25 to 2024-02-26
[31 empty] | Supplier | ADS/SDS | Metering (Allocated to Service User) | Service User (can use any of the roles) | LDSO
[31 empty] | E.ON Next | Octopus/Kraken | E.ON UK Energy Services/Wheatley | Utilita | BUUK
[31 empty] | Utilita | IMServ |  | PDA | SSEN
British Gas
Octopus/Kraken