## Cover Page
MHHS M10/M11 Cutover Delivery Plan
Document owner: | Document number: | Version:
MHHS Transition & Operational Readiness Team | MHHS-DEL2522 | 2.1
Status: | Date: | Classification:
Baselined following MCAG Approval | 2025-09-08 | External

## Introduction
Document Purpose
This document outlines each individual activity that is included within the Cutover plan including when it is due to take place and who is responsible for it. This document is intended to act as the list of activities that will need to by participants in the lead up to and during the Cutover period.
Objectives
The document aims to: - Establish a clear timeline with milestones for the Cutover period - Identify key dependencies between activities - Serve as a central communication tool that stakeholders can refer to throughout the Cutover period
Delivery Plan
Column Name | Description of the data in each of the columns within Delivery Plan worksheet
Category | Cutover tasks required for completion
Cutover WBS | Hierarchical breakdown of cutover tasks
Cutover Plan Reference | Task reference number from MHHS-DEL2521 - MHHS M10/M11 Cutover Plan
Activity | Cutover tasks required for completion
Responsible Party | Party responsible for executing each sub-activity
Cutover Dependencies | Activities that must be completed before a particular activity can start
Start Date | Planned start date for an activity
Due Date | Planned due date for completing an activity

## Consolidated Delivery Plan
Days
Category | Cutover WBS | Cutover Plan Reference | Activity | Responsible Parties | Cutover Dependencies | Start Date | Due Date | Baseline Start Date | time axis 2025-01-01 to 2026-03-11
Test Completion | 1.1 | N/A | SIT MVC Test Exit Report Approved | SIT MVC Participants, MHHS Programme |  | 2025-08-22 | 2025-08-22 | bar: 2025-08-22
| 1.2 | N/A | Settlement Assurance Testing | Helix, MHHS Programme |  | 2024 | 2025-08-07 | bar: 2025-01-01 to 2025-08-07
Pre-M10 | 2.1 | 6.1 | Elexon Services | Elexon |  | 2025-06-27 | 2025-09-22 |  | 2025-06-27: p; 2025-06-28: g; 2025-06-29: g; 2025-06-30: g; 2025-07-01: g; 2025-07-02: g; 2025-07-03: g; 2025-07-04: g; 2025-07-05: g; 2025-07-06: g; 2025-07-07: g; 2025-07-08: g; 2025-07-09: g; 2025-07-10: g; 2025-07-11: g; 2025-07-12: g; 2025-07-13: g; 2025-07-14: g; 2025-07-15: g; 2025-07-16: g; 2025-07-17: g; 2025-07-18: g; 2025-07-19: g; 2025-07-20: g; 2025-07-21: g; 2025-07-22: g; 2025-07-23: g; 2025-07-24: g; 2025-07-25: g; 2025-07-26: g; 2025-07-27: g; 2025-07-28: g; 2025-07-29: g; 2025-07-30: g; 2025-07-31: g; 2025-08-01: g; 2025-08-02: g; 2025-08-03: g; 2025-08-04: g; 2025-08-05: g; 2025-08-06: g; 2025-08-07: g; 2025-08-08: g; 2025-08-09: g; 2025-08-10: g; 2025-08-11: g; 2025-08-12: g; 2025-08-13: g; 2025-08-14: g; 2025-08-15: g; 2025-08-16: g; 2025-08-17: g; 2025-08-18: g; 2025-08-19: g; 2025-08-20: g; 2025-08-21: g; 2025-08-22: g; 2025-08-23: g; 2025-08-24: g; 2025-08-25: g; 2025-08-26: g; 2025-08-27: g; 2025-08-28: g; 2025-08-29: g; 2025-08-30: g; 2025-08-31: g; 2025-09-01: g; 2025-09-02: g; 2025-09-03: g; 2025-09-04: g; 2025-09-05: g; 2025-09-06: g; 2025-09-07: g; 2025-09-08: g; 2025-09-09: g; 2025-09-10: g; 2025-09-11: g; 2025-09-12: g; 2025-09-13: g; 2025-09-14: g; 2025-09-15: g; 2025-09-16: g; 2025-09-17: g; 2025-09-18: g; 2025-09-19: g; 2025-09-20: g; 2025-09-21: g; 2025-09-22: q
| 2.1.1 | 6.1.1 | Load Shaping Service (LSS) | Elexon and Elexon Service Providers | There is a dependency on the successful completion of the System Integration Test Report (SIT) before the environment can be considered ready for use. Any remaining priority defects out of SIT will be risk-assessed and a business decision will be made to create, test and deploy a fix to the DIP Production Environment, or to resolve as part of product backlog development post M10. | 2025-07-14 | 2025-07-25 |  | 2025-07-14: p; 2025-07-15: g; 2025-07-16: g; 2025-07-17: g; 2025-07-18: g; 2025-07-19: g; 2025-07-20: g; 2025-07-21: g; 2025-07-22: g; 2025-07-23: g; 2025-07-24: g; 2025-07-25: q
| 2.1.2 | 6.1.2 | Volume Allocation Service (VAS) | Elexon and Elexon Service Providers | There is a dependency on the successful completion of the System Integration Test Report (SIT) before the environment can be considered ready for use. Any remaining priority defects out of SIT will be risk-assessed and a business decision will be made to create, test and deploy a fix to the DIP Production Environment, or to resolve as part of product backlog development post M10. | 2025-07-14 | 2025-07-25 |  | 2025-07-14: p; 2025-07-15: g; 2025-07-16: g; 2025-07-17: g; 2025-07-18: g; 2025-07-19: g; 2025-07-20: g; 2025-07-21: g; 2025-07-22: g; 2025-07-23: g; 2025-07-24: g; 2025-07-25: q
| 2.1.3 | 6.1.3 | Market-wide Data Service (MDS) | Elexon and Elexon Service Providers | There is a dependency on the successful completion of the System Integration Test Report (SIT) before the environment can be considered ready for use. Any remaining priority defects out of SIT will be risk-assessed and a business decision will be made to create, test and deploy a fix to the DIP Production Environment, or to resolve as part of product backlog development post M10. | 2025-07-14 | 2025-07-25 |  | 2025-07-14: p; 2025-07-15: g; 2025-07-16: g; 2025-07-17: g; 2025-07-18: g; 2025-07-19: g; 2025-07-20: g; 2025-07-21: g; 2025-07-22: g; 2025-07-23: g; 2025-07-24: g; 2025-07-25: q
| 2.1.4 | 6.1.4 | Deployment of Industry Standing Data (ISD) Work Package (WP3) source code | Elexon and Elexon Service Providers | There is a dependency on the successful completion of the System Integration Test Report (SIT) before the environment can be considered ready for use. Any remaining priority defects out of SIT will be risk-assessed and a business decision will be made to create, test and deploy a fix to the DIP Production Environment, or to resolve as part of product backlog development post M10. | 2025-07-14 | 2025-07-25 |  | 2025-07-14: p; 2025-07-15: g; 2025-07-16: g; 2025-07-17: g; 2025-07-18: g; 2025-07-19: g; 2025-07-20: g; 2025-07-21: g; 2025-07-22: g; 2025-07-23: g; 2025-07-24: g; 2025-07-25: q
| 2.1.5 | 6.1.4 | ISD Service Activation | Elexon and Elexon Service Providers |  | 2025-08-05 | 2025-08-05 | bar: 2025-08-05
| 2.1.6 | 6.1.4 | ISD Data Migration (PR-3) | Elexon and Elexon Service Providers |  | 2025-08-05 | 2025-08-12 |  | 2025-08-05: p; 2025-08-06: g; 2025-08-07: g; 2025-08-08: g; 2025-08-09: g; 2025-08-10: g; 2025-08-11: g; 2025-08-12: q
| 2.1.7 | 6.1.4 | ISD Data Migration (PR-4) | Elexon and Elexon Service Providers |  | 2025-08-15 | 2025-08-22 |  | 2025-08-15: p; 2025-08-16: g; 2025-08-17: g; 2025-08-18: g; 2025-08-19: g; 2025-08-20: g; 2025-08-21: g; 2025-08-22: q
| 2.1.8 | 6.1.4 | ISD Catalogue Published | Elexon and Elexon Service Providers |  | 2025-09-11 | 2025-09-11 | bar: 2025-09-11
| 2.1.9 | 6.1.4 | IF-047 Broadcast | Elexon and Elexon Service Providers |  | 2025-09-22 | 2025-09-22 | bar: 2025-09-22
| 2.1.10 | 6.1.5 | DIP Production Environment stood up | DIP Manager, Elexon |  | 2025-07-18 | 2025-07-18 | bar: 2025-07-18
| 2.1.11 | 6.1.5 | Production DIP Portal (DIP Deployment) | DIP Manager, Elexon | In order for the DIP Production Portal to be made available to Participants there is a dependency on an Elexon managed Service Management wrapper being in place. | 2025-08-01 | 2025-08-04 |  | 2025-08-01: p; 2025-08-02: g; 2025-08-03: g; 2025-08-04: q
| 2.1.12 | 6.1.5 | Production Certificates (DIP Deployment) | DIP Manager, Elexon | In order for the Production Certificates to be made available to Participants there is a dependency on an Elexon managed Service Management wrapper being in place. | 2025-08-01 | 2025-08-04 |  | 2025-08-01: p; 2025-08-02: g; 2025-08-03: g; 2025-08-04: q
| 2.1.13 | 6.1.6 | Service Management Go-Live | Elexon | The completion of Service Design by Elexon | 2025-07-31 | 2025-07-31 | bar: 2025-07-31
| 2.2 | 6.2 | Code Bodies - Qualification |  | The qualification of each party following this pathway will be a key dependency for the success of M10. | 2025-07-18 | 2025-10-16 |  | 2025-07-18: p; 2025-07-19: g; 2025-07-20: g; 2025-07-21: g; 2025-07-22: g; 2025-07-23: g; 2025-07-24: g; 2025-07-25: g; 2025-07-26: g; 2025-07-27: g; 2025-07-28: g; 2025-07-29: g; 2025-07-30: g; 2025-07-31: g; 2025-08-01: g; 2025-08-02: g; 2025-08-03: g; 2025-08-04: g; 2025-08-05: g; 2025-08-06: g; 2025-08-07: g; 2025-08-08: g; 2025-08-09: g; 2025-08-10: g; 2025-08-11: g; 2025-08-12: g; 2025-08-13: g; 2025-08-14: g; 2025-08-15: g; 2025-08-16: g; 2025-08-17: g; 2025-08-18: g; 2025-08-19: g; 2025-08-20: g; 2025-08-21: g; 2025-08-22: g; 2025-08-23: g; 2025-08-24: g; 2025-08-25: g; 2025-08-26: g; 2025-08-27: g; 2025-08-28: g; 2025-08-29: g; 2025-08-30: g; 2025-08-31: g; 2025-09-01: g; 2025-09-02: g; 2025-09-03: g; 2025-09-04: g; 2025-09-05: g; 2025-09-06: g; 2025-09-07: g; 2025-09-08: g; 2025-09-09: g; 2025-09-10: g; 2025-09-11: g; 2025-09-12: g; 2025-09-13: g; 2025-09-14: g; 2025-09-15: g; 2025-09-16: g; 2025-09-17: g; 2025-09-18: g; 2025-09-19: g; 2025-09-20: g; 2025-09-21: g; 2025-09-22: g; 2025-09-23: g; 2025-09-24: g; 2025-09-25: g; 2025-09-26: g; 2025-09-27: g; 2025-09-28: g; 2025-09-29: g; 2025-09-30: g; 2025-10-01: g; 2025-10-02: g; 2025-10-03: g; 2025-10-04: g; 2025-10-05: g; 2025-10-06: g; 2025-10-07: g; 2025-10-08: g; 2025-10-09: g; 2025-10-10: g; 2025-10-11: g; 2025-10-12: g; 2025-10-13: g; 2025-10-14: g; 2025-10-15: g; 2025-10-16: q
| 2.2.1 | 6.2.1 | Qualification Pathway 1
Qualification Pathway 1 is no longer viable. It has been included here to avoid confusion with naming conventions.
| 2.2.2 | 6.2.2 | Qualification Pathway 2 | REC Code Manager, BSC PAB, DIP Manager, SIT Participants, LDSOs, MHHS Programme |  | 2025-07-18 | 2025-08-29 |  | 2025-07-18: p; 2025-07-19: g; 2025-07-20: g; 2025-07-21: g; 2025-07-22: g; 2025-07-23: g; 2025-07-24: g; 2025-07-25: g; 2025-07-26: g; 2025-07-27: g; 2025-07-28: g; 2025-07-29: g; 2025-07-30: g; 2025-07-31: g; 2025-08-01: g; 2025-08-02: g; 2025-08-03: g; 2025-08-04: g; 2025-08-05: g; 2025-08-06: g; 2025-08-07: g; 2025-08-08: g; 2025-08-09: g; 2025-08-10: g; 2025-08-11: g; 2025-08-12: g; 2025-08-13: g; 2025-08-14: g; 2025-08-15: g; 2025-08-16: g; 2025-08-17: g; 2025-08-18: g; 2025-08-19: g; 2025-08-20: g; 2025-08-21: g; 2025-08-22: g; 2025-08-23: g; 2025-08-24: g; 2025-08-25: g; 2025-08-26: g; 2025-08-27: g; 2025-08-28: g; 2025-08-29: q
| 2.2.2.1 | 6.2.2.1 | Complete SIT | Participant |  | 2025-07-18 | 2025-07-18 | bar: 2025-07-18
| 2.2.2.2 | 6.2.2.2 | PP Exits SIT (Programme drafts and approves PP’s Regression Completion Pro Forma) | Participant |  | 2025-07-21 | 2025-07-28 |  | 2025-07-21: p; 2025-07-22: g; 2025-07-23: g; 2025-07-24: g; 2025-07-25: g; 2025-07-26: g; 2025-07-27: g; 2025-07-28: q
| 2.2.2.3 | 6.2.2.3 | PP submits SIT completion in QAD | Participant |  | 2025-07-29 | 2025-08-04 |  | 2025-07-29: p; 2025-07-30: g; 2025-07-31: g; 2025-08-01: g; 2025-08-02: g; 2025-08-03: g; 2025-08-04: q
| 2.2.2.4 | 6.2.2.4 | QAD Sign off by Director | Participant |  | 2025-08-04 | 2025-08-07 |  | 2025-08-04: p; 2025-08-05: g; 2025-08-06: g; 2025-08-07: q
| 2.2.2.5 | 6.2.2.5 | QSP Finalise Report & Issue to BSC Qual Team & DIP Manager | QSP (Elexon) |  | 2025-08-07 | 2025-08-13 |  | 2025-08-07: p; 2025-08-08: g; 2025-08-09: g; 2025-08-10: g; 2025-08-11: g; 2025-08-12: g; 2025-08-13: q
| 2.2.2.6 | 6.2.2.6 | DIP Manager Checklist | DIP Manager |  | 2025-08-14 | 2025-08-19 |  | 2025-08-14: p; 2025-08-15: g; 2025-08-16: g; 2025-08-17: g; 2025-08-18: g; 2025-08-19: q
| 2.2.2.7 | 6.2.2.7 | REC Code Manager review follow-up and Qualification decision | REC Code Manager |  | 2025-08-07 | 2025-08-28 |  | 2025-08-07: p; 2025-08-08: g; 2025-08-09: g; 2025-08-10: g; 2025-08-11: g; 2025-08-12: g; 2025-08-13: g; 2025-08-14: g; 2025-08-15: g; 2025-08-16: g; 2025-08-17: g; 2025-08-18: g; 2025-08-19: g; 2025-08-20: g; 2025-08-21: g; 2025-08-22: g; 2025-08-23: g; 2025-08-24: g; 2025-08-25: g; 2025-08-26: g; 2025-08-27: g; 2025-08-28: q
| 2.2.2.8 | 6.2.2.8 | BSC Qual Team Review + Recommendation | BSC |  | 2025-08-14 | 2025-08-19 |  | 2025-08-14: p; 2025-08-15: g; 2025-08-16: g; 2025-08-17: g; 2025-08-18: g; 2025-08-19: q
| 2.2.2.9 | 6.2.2.9 | BSC PAB Chair review | BSC |  | 2025-08-20 | 2025-08-21 | bar: 2025-08-20 to 2025-08-21
| 2.2.2.10 | 6.2.2.10 | Submit SIT PP for BSC PAB Paper Day | BSC |  | 2025-08-21 | 2025-08-21 | bar: 2025-08-21
| 2.2.2.11 | 6.2.2.11 | BSC PAB / REC Code Manager Approval | BSC |  | 2025-08-28 | 2025-08-28 | bar: 2025-08-28
| 2.2.2.12 | 6.2.2.12 | Notification to PP and Elexon | REC Code Manager |  | 2025-08-29 | 2025-08-29 | bar: 2025-08-29
| 2.2.3 | 6.2.3 | Qualification Pathway 3 | REC Code Manager, BSC PAB, DIP Manager, SIT Participants, LDSOs, MHHS Programme |  | 2025-08-08 | 2025-09-11 |  | 2025-08-08: p; 2025-08-09: g; 2025-08-10: g; 2025-08-11: g; 2025-08-12: g; 2025-08-13: g; 2025-08-14: g; 2025-08-15: g; 2025-08-16: g; 2025-08-17: g; 2025-08-18: g; 2025-08-19: g; 2025-08-20: g; 2025-08-21: g; 2025-08-22: g; 2025-08-23: g; 2025-08-24: g; 2025-08-25: g; 2025-08-26: g; 2025-08-27: g; 2025-08-28: g; 2025-08-29: g; 2025-08-30: g; 2025-08-31: g; 2025-09-01: g; 2025-09-02: g; 2025-09-03: g; 2025-09-04: g; 2025-09-05: g; 2025-09-06: g; 2025-09-07: g; 2025-09-08: g; 2025-09-09: g; 2025-09-10: g; 2025-09-11: q
| 2.2.3.1 | 6.2.3.1 | Complete SIT | Participant |  | 2025-08-08 | 2025-08-08 | bar: 2025-08-08
| 2.2.3.2 | 6.2.3.2 | PP Exits SIT (Programme drafts and approves PP’s Regression Completion Pro Forma) | Participant |  | 2025-08-11 | 2025-08-15 |  | 2025-08-11: p; 2025-08-12: g; 2025-08-13: g; 2025-08-14: g; 2025-08-15: q
| 2.2.3.3 | 6.2.3.3 | PP submits SIT completion in QAD | Participant |  | 2025-08-18 | 2025-08-22 |  | 2025-08-18: p; 2025-08-19: g; 2025-08-20: g; 2025-08-21: g; 2025-08-22: q
| 2.2.3.4 | 6.2.3.4 | QAD Sign off by Director | Participant |  | 2025-08-18 | 2025-08-22 |  | 2025-08-18: p; 2025-08-19: g; 2025-08-20: g; 2025-08-21: g; 2025-08-22: q
| 2.2.3.5 | 6.2.3.5 | QSP Finalise Report & Issue to BSC Qual Team & DIP Manager | QSP (Elexon) |  | 2025-08-26 | 2025-08-28 |  | 2025-08-26: p; 2025-08-27: g; 2025-08-28: q
| 2.2.3.6 | 6.2.3.6 | DIP Manager Checklist | DIP Manager |  | 2025-08-29 | 2025-09-02 |  | 2025-08-29: p; 2025-08-30: g; 2025-08-31: g; 2025-09-01: g; 2025-09-02: q
| 2.2.3.7 | 6.2.3.7 | REC Code Manager review follow-up and Qualification decision | REC Code Manager |  | 2025-08-26 | 2025-09-10 |  | 2025-08-26: p; 2025-08-27: g; 2025-08-28: g; 2025-08-29: g; 2025-08-30: g; 2025-08-31: g; 2025-09-01: g; 2025-09-02: g; 2025-09-03: g; 2025-09-04: g; 2025-09-05: g; 2025-09-06: g; 2025-09-07: g; 2025-09-08: g; 2025-09-09: g; 2025-09-10: q
| 2.2.3.8 | 6.2.3.8 | BSC Qual Team Review + Recommendation | BSC |  | 2025-08-29 | 2025-09-02 |  | 2025-08-29: p; 2025-08-30: g; 2025-08-31: g; 2025-09-01: g; 2025-09-02: q
| 2.2.3.9 | 6.2.3.9 | BSC PAB Chair review | BSC |  | 2025-09-03 | 2025-09-04 | bar: 2025-09-03 to 2025-09-04
| 2.2.3.10 | 6.2.3.10 | Submit SIT PP for BSC PAB Paper Day | BSC |  | 2025-09-04 | 2025-09-04 | bar: 2025-09-04
| 2.2.3.11 | 6.2.3.11 | BSC PAB / REC Code Manager Approval | BSC |  | 2025-09-09 | 2025-09-10 | bar: 2025-09-09 to 2025-09-10
| 2.2.3.12 | 6.2.3.12 | Notification to PP and Elexon | REC Code Manager |  | 2025-09-11 | 2025-09-11 | bar: 2025-09-11
| 2.2.4 | 6.2.4 | Qualification Pathway 4 | REC Code Manager, BSC PAB, DIP Manager, SIT Participants, MHHS Programme |  | 2025-08-15 | 2025-09-26 |  | 2025-08-15: p; 2025-08-16: g; 2025-08-17: g; 2025-08-18: g; 2025-08-19: g; 2025-08-20: g; 2025-08-21: g; 2025-08-22: g; 2025-08-23: g; 2025-08-24: g; 2025-08-25: g; 2025-08-26: g; 2025-08-27: g; 2025-08-28: g; 2025-08-29: g; 2025-08-30: g; 2025-08-31: g; 2025-09-01: g; 2025-09-02: g; 2025-09-03: g; 2025-09-04: g; 2025-09-05: g; 2025-09-06: g; 2025-09-07: g; 2025-09-08: g; 2025-09-09: g; 2025-09-10: g; 2025-09-11: g; 2025-09-12: g; 2025-09-13: g; 2025-09-14: g; 2025-09-15: g; 2025-09-16: g; 2025-09-17: g; 2025-09-18: g; 2025-09-19: g; 2025-09-20: g; 2025-09-21: g; 2025-09-22: g; 2025-09-23: g; 2025-09-24: g; 2025-09-25: g; 2025-09-26: q
| 2.2.4.1 | 6.2.4.1 | Complete SIT | Participant |  | 2025-08-15 | 2025-08-15 | bar: 2025-08-15
| 2.2.4.2 | 6.2.4.2 | PP Exits SIT (Programme drafts and approves PP’s Regression Completion Pro Forma) | Participant |  | 2025-08-15 | 2025-08-22 |  | 2025-08-15: p; 2025-08-16: g; 2025-08-17: g; 2025-08-18: g; 2025-08-19: g; 2025-08-20: g; 2025-08-21: g; 2025-08-22: q
| 2.2.4.3 | 6.2.4.3 | PP submits SIT completion in QAD | Participant |  | 2025-08-25 | 2025-08-28 |  | 2025-08-25: p; 2025-08-26: g; 2025-08-27: g; 2025-08-28: q
| 2.2.4.4 | 6.2.4.4 | QAD Sign off by Director | Participant |  | 2025-09-01 | 2025-09-02 | bar: 2025-09-01 to 2025-09-02
| 2.2.4.5 | 6.2.4.5 | QSP Finalise Report & Issue to BSC Qual Team & DIP Manager | QSP (Elexon) |  | 2025-09-03 | 2025-09-09 |  | 2025-09-03: p; 2025-09-04: g; 2025-09-05: g; 2025-09-06: g; 2025-09-07: g; 2025-09-08: g; 2025-09-09: q
| 2.2.4.6 | 6.2.4.6 | DIP Manager Checklist | DIP Manager |  | 2025-09-10 | 2025-09-16 |  | 2025-09-10: p; 2025-09-11: g; 2025-09-12: g; 2025-09-13: g; 2025-09-14: g; 2025-09-15: g; 2025-09-16: q
| 2.2.4.7 | 6.2.4.7 | REC Code Manager review follow-up and Qualification decision | REC Code Manager |  | 2025-09-03 | 2025-09-25 |  | 2025-09-03: p; 2025-09-04: g; 2025-09-05: g; 2025-09-06: g; 2025-09-07: g; 2025-09-08: g; 2025-09-09: g; 2025-09-10: g; 2025-09-11: g; 2025-09-12: g; 2025-09-13: g; 2025-09-14: g; 2025-09-15: g; 2025-09-16: g; 2025-09-17: g; 2025-09-18: g; 2025-09-19: g; 2025-09-20: g; 2025-09-21: g; 2025-09-22: g; 2025-09-23: g; 2025-09-24: g; 2025-09-25: q
| 2.2.4.8 | 6.2.4.8 | BSC Qual Team Review + Recommendation | BSC |  | 2025-09-10 | 2025-09-16 |  | 2025-09-10: p; 2025-09-11: g; 2025-09-12: g; 2025-09-13: g; 2025-09-14: g; 2025-09-15: g; 2025-09-16: q
| 2.2.4.9 | 6.2.4.9 | BSC PAB Chair review | BSC |  | 2025-09-17 | 2025-09-18 | bar: 2025-09-17 to 2025-09-18
| 2.2.4.10 | 6.2.4.10 | Submit SIT PP for BSC PAB Paper Day | BSC |  | 2025-09-18 | 2025-09-18 | bar: 2025-09-18
| 2.2.4.11 | 6.2.4.11 | BSC PAB / REC Code Manager Approval | BSC |  | 2025-09-25 | 2025-09-25 | bar: 2025-09-25
| 2.2.4.12 | 6.2.4.12 | Notification to PP and Elexon | REC Code Manager |  | 2025-09-26 | 2025-09-26 | bar: 2025-09-26
| 2.2.5 | 6.2.5 | Qualification Pathway 5 | REC Code Manager, BSC PAB, DIP Manager, SIT Participants, MHHS Programme |  | 2025-09-05 | 2025-10-16 |  | 2025-09-05: p; 2025-09-06: g; 2025-09-07: g; 2025-09-08: g; 2025-09-09: g; 2025-09-10: g; 2025-09-11: g; 2025-09-12: g; 2025-09-13: g; 2025-09-14: g; 2025-09-15: g; 2025-09-16: g; 2025-09-17: g; 2025-09-18: g; 2025-09-19: g; 2025-09-20: g; 2025-09-21: g; 2025-09-22: g; 2025-09-23: g; 2025-09-24: g; 2025-09-25: g; 2025-09-26: g; 2025-09-27: g; 2025-09-28: g; 2025-09-29: g; 2025-09-30: g; 2025-10-01: g; 2025-10-02: g; 2025-10-03: g; 2025-10-04: g; 2025-10-05: g; 2025-10-06: g; 2025-10-07: g; 2025-10-08: g; 2025-10-09: g; 2025-10-10: g; 2025-10-11: g; 2025-10-12: g; 2025-10-13: g; 2025-10-14: g; 2025-10-15: g; 2025-10-16: q
| 2.2.5.1 | 6.2.5.1 | Complete SIT | Participant |  | 2025-09-05 | 2025-09-05 | bar: 2025-09-05
| 2.2.5.2 | 6.2.5.2 | PP Exits SIT (Programme drafts and approves PP’s Regression Completion Pro Forma) | Participant |  | 2025-09-05 | 2025-09-12 |  | 2025-09-05: p; 2025-09-06: g; 2025-09-07: g; 2025-09-08: g; 2025-09-09: g; 2025-09-10: g; 2025-09-11: g; 2025-09-12: q
| 2.2.5.3 | 6.2.5.3 | PP submits SIT completion in QAD | Participant |  | 2025-09-15 | 2025-09-18 |  | 2025-09-15: p; 2025-09-16: g; 2025-09-17: g; 2025-09-18: q
| 2.2.5.4 | 6.2.5.4 | QAD Sign off by Director | Participant |  | 2025-09-22 | 2025-09-23 | bar: 2025-09-22 to 2025-09-23
| 2.2.5.5 | 6.2.5.5 | QSP Finalise Report & Issue to BSC Qual Team & DIP Manager | QSP (Elexon) |  | 2025-09-24 | 2025-10-01 |  | 2025-09-24: p; 2025-09-25: g; 2025-09-26: g; 2025-09-27: g; 2025-09-28: g; 2025-09-29: g; 2025-09-30: g; 2025-10-01: q
| 2.2.5.6 | 6.2.5.6 | DIP Manager Checklist | DIP Manager |  | 2025-10-02 | 2025-10-07 |  | 2025-10-02: p; 2025-10-03: g; 2025-10-04: g; 2025-10-05: g; 2025-10-06: g; 2025-10-07: q
| 2.2.5.7 | 6.2.5.7 | REC Code Manager review follow-up and Qualification decision | REC Code Manager |  | 2025-09-24 | 2025-10-15 |  | 2025-09-24: p; 2025-09-25: g; 2025-09-26: g; 2025-09-27: g; 2025-09-28: g; 2025-09-29: g; 2025-09-30: g; 2025-10-01: g; 2025-10-02: g; 2025-10-03: g; 2025-10-04: g; 2025-10-05: g; 2025-10-06: g; 2025-10-07: g; 2025-10-08: g; 2025-10-09: g; 2025-10-10: g; 2025-10-11: g; 2025-10-12: g; 2025-10-13: g; 2025-10-14: g; 2025-10-15: q
| 2.2.5.8 | 6.2.5.8 | BSC Qual Team Review + Recommendation | BSC |  | 2025-10-01 | 2025-10-07 |  | 2025-10-01: p; 2025-10-02: g; 2025-10-03: g; 2025-10-04: g; 2025-10-05: g; 2025-10-06: g; 2025-10-07: q
| 2.2.5.9 | 6.2.5.9 | BSC PAB Chair review | BSC |  | 2025-10-08 | 2025-10-09 | bar: 2025-10-08 to 2025-10-09
| 2.2.5.10 | 6.2.5.10 | Submit SIT PP for BSC PAB Paper Day | BSC |  | 2025-10-09 | 2025-10-09 | bar: 2025-10-09
| 2.2.5.11 | 6.2.5.11 | BSC PAB / REC Code Manager Approval | BSC |  | 2025-10-15 | 2025-10-15 | bar: 2025-10-15
| 2.2.5.12 | 6.2.5.12 | Notification to PP and Elexon | REC Code Manager |  | 2025-10-16 | 2025-10-16 | bar: 2025-10-16
| 2.3 | 6.3 | LDSOs |  |  | 2025-08-04 | 2025-09-11 |  | 2025-08-04: p; 2025-08-05: g; 2025-08-06: g; 2025-08-07: g; 2025-08-08: g; 2025-08-09: g; 2025-08-10: g; 2025-08-11: g; 2025-08-12: g; 2025-08-13: g; 2025-08-14: g; 2025-08-15: g; 2025-08-16: g; 2025-08-17: g; 2025-08-18: g; 2025-08-19: g; 2025-08-20: g; 2025-08-21: g; 2025-08-22: g; 2025-08-23: g; 2025-08-24: g; 2025-08-25: g; 2025-08-26: g; 2025-08-27: g; 2025-08-28: g; 2025-08-29: g; 2025-08-30: g; 2025-08-31: g; 2025-09-01: g; 2025-09-02: g; 2025-09-03: g; 2025-09-04: g; 2025-09-05: g; 2025-09-06: g; 2025-09-07: g; 2025-09-08: g; 2025-09-09: g; 2025-09-10: g; 2025-09-11: q
| 2.3.1 | 6.3.1 | DIP Onboarding | LDSOs, DIP Manager | To enable DIP onboarding, there is a dependency on the DIP Portal being available to participants and Elexon Service Management systems, processes and user access to be deployed by the 4th August 2025. There is a dependency on the DIP Manager making changes to the DIP Rules to enable LDSOs to onboard to the DIP ahead of MHHS qualification. This rule change will only be in place until MHHS go-live. | 2025-08-04 | 2025-08-22 |  | 2025-08-04: p; 2025-08-05: g; 2025-08-06: g; 2025-08-07: g; 2025-08-08: g; 2025-08-09: g; 2025-08-10: g; 2025-08-11: g; 2025-08-12: g; 2025-08-13: g; 2025-08-14: g; 2025-08-15: g; 2025-08-16: g; 2025-08-17: g; 2025-08-18: g; 2025-08-19: g; 2025-08-20: g; 2025-08-21: g; 2025-08-22: q
| 2.3.2 | 6.3.2 | Deployment of MPRS 9 | LDSOs, St Clements | All LDSOs will require the production ready version of MPRS 9 to be shared with them by St Clements during w/c 4th August. | 2025-08-06 | 2025-09-01 |  | 2025-08-06: p; 2025-08-07: g; 2025-08-08: g; 2025-08-09: g; 2025-08-10: g; 2025-08-11: g; 2025-08-12: g; 2025-08-13: g; 2025-08-14: g; 2025-08-15: g; 2025-08-16: g; 2025-08-17: g; 2025-08-18: g; 2025-08-19: g; 2025-08-20: g; 2025-08-21: g; 2025-08-22: g; 2025-08-23: g; 2025-08-24: g; 2025-08-25: g; 2025-08-26: g; 2025-08-27: g; 2025-08-28: g; 2025-08-29: g; 2025-08-30: g; 2025-08-31: g; 2025-09-01: q
| 2.3.3 | 6.3.3 | ISD Population | LDSOs | The ISD file will need to be made available via the Elexon portal by 11/09/2025 | 2025-09-11 | 2025-09-11 | bar: 2025-09-11
| 2.4 | 6.4 | Population of Market Segment and Domestic Premises Indicator |  |  | 2025-08-06 | 2025-09-22 |  | 2025-08-06: p; 2025-08-07: g; 2025-08-08: g; 2025-08-09: g; 2025-08-10: g; 2025-08-11: g; 2025-08-12: g; 2025-08-13: g; 2025-08-14: g; 2025-08-15: g; 2025-08-16: g; 2025-08-17: g; 2025-08-18: g; 2025-08-19: g; 2025-08-20: g; 2025-08-21: g; 2025-08-22: g; 2025-08-23: g; 2025-08-24: g; 2025-08-25: g; 2025-08-26: g; 2025-08-27: g; 2025-08-28: g; 2025-08-29: g; 2025-08-30: g; 2025-08-31: g; 2025-09-01: g; 2025-09-02: g; 2025-09-03: g; 2025-09-04: g; 2025-09-05: g; 2025-09-06: g; 2025-09-07: g; 2025-09-08: g; 2025-09-09: g; 2025-09-10: g; 2025-09-11: g; 2025-09-12: g; 2025-09-13: g; 2025-09-14: g; 2025-09-15: g; 2025-09-16: g; 2025-09-17: g; 2025-09-18: g; 2025-09-19: g; 2025-09-20: g; 2025-09-21: g; 2025-09-22: q
| 2.4.1 | 6.4.1 | Population of Market Segment (95%) | LDSOs, St Clements | LDSOs have been able to verify that the population process developed by St Clements can populate Market Segments at the requisite speeds for them to be able to meet the deadlines set out above. | 2025-08-06 | 2025-09-12 |  | 2025-08-06: p; 2025-08-07: g; 2025-08-08: g; 2025-08-09: g; 2025-08-10: g; 2025-08-11: g; 2025-08-12: g; 2025-08-13: g; 2025-08-14: g; 2025-08-15: g; 2025-08-16: g; 2025-08-17: g; 2025-08-18: g; 2025-08-19: g; 2025-08-20: g; 2025-08-21: g; 2025-08-22: g; 2025-08-23: g; 2025-08-24: g; 2025-08-25: g; 2025-08-26: g; 2025-08-27: g; 2025-08-28: g; 2025-08-29: g; 2025-08-30: g; 2025-08-31: g; 2025-09-01: g; 2025-09-02: g; 2025-09-03: g; 2025-09-04: g; 2025-09-05: g; 2025-09-06: g; 2025-09-07: g; 2025-09-08: g; 2025-09-09: g; 2025-09-10: g; 2025-09-11: g; 2025-09-12: q
| 2.4.2 | 6.4.1 | Population of Market Segment (100%) | LDSOs, St Clements | LDSOs have been able to verify that the population process developed by St Clements can populate Market Segments at the requisite speeds for them to be able to meet the deadlines set out above. | 2025-09-12 | 2025-09-22 |  | 2025-09-12: p; 2025-09-13: g; 2025-09-14: g; 2025-09-15: g; 2025-09-16: g; 2025-09-17: g; 2025-09-18: g; 2025-09-19: g; 2025-09-20: g; 2025-09-21: g; 2025-09-22: q
| 2.4.3 | 6.4.2 | Population of Domestic Premises Indicator | LDSOs, DCC, St Clements, RECCo (EES) | St Clements have developed a script that allows LDSOs to populate Domestic Premises Indicator for each MPAN in their portfolio using the extract shared with them by the Programme and this process has been tested on the dates set out within the Data Cleanse Plan. | 2025-09-06 | 2025-09-08 |  | 2025-09-06: p; 2025-09-07: g; 2025-09-08: q
| 2.5 | 6.5 | Completion of the pre-M10 MHHS Data Cleanse | Suppliers, LDSOs, MEMs, DCC, MHHS Programme SI | There is a dependency on Programme Participants carrying out the activities that they are responsible for as set out within the Data Cleanse Plan. | 2024 | 2025-09-22 | bar: 2025-01-01 to 2025-09-22
| 2.6 | 6.6 | Early Life Support Implemented | MHHS Programme, Elexon, Central Services, LDSOs | There is a dependency on all parties identified within the ELS Model having the relevant reporting in place to support the approach set out within the model and to have identified the relevant staff to attend governance meetings and provide updates to the Programme. | 2024 | 2025-09-19 | bar: 2025-01-01 to 2025-09-19
| 2.7 | 6.7 | MCC Tested and Ready to Operate | MHHS Programme Migration Team | Having the Migration Control Centre operational is a key dependency for the MHHS Migration period as it will be required to allocate migration capacity to participants and manage the industry-wide Migration Plan. | 2025-08-08 | 2025-09-19 |  | 2025-08-08: p; 2025-08-09: g; 2025-08-10: g; 2025-08-11: g; 2025-08-12: g; 2025-08-13: g; 2025-08-14: g; 2025-08-15: g; 2025-08-16: g; 2025-08-17: g; 2025-08-18: g; 2025-08-19: g; 2025-08-20: g; 2025-08-21: g; 2025-08-22: g; 2025-08-23: g; 2025-08-24: g; 2025-08-25: g; 2025-08-26: g; 2025-08-27: g; 2025-08-28: g; 2025-08-29: g; 2025-08-30: g; 2025-08-31: g; 2025-09-01: g; 2025-09-02: g; 2025-09-03: g; 2025-09-04: g; 2025-09-05: g; 2025-09-06: g; 2025-09-07: g; 2025-09-08: g; 2025-09-09: g; 2025-09-10: g; 2025-09-11: g; 2025-09-12: g; 2025-09-13: g; 2025-09-14: g; 2025-09-15: g; 2025-09-16: g; 2025-09-17: g; 2025-09-18: g; 2025-09-19: q
| 2.8 | 6.8 | Market-wide Participant MHHS Supporting Functionality | Suppliers, MOPs and DCs |  | 2024 | 2025-09-22 | bar: 2025-01-01 to 2025-09-22
| 2.8.1 | 6.8 | Market-wide Participant MHHS Supporting Functionality Ready - Confirmation from Code Bodies | Code Bodies |  | 2024 | 2025-09-15 | bar: 2025-01-01 to 2025-09-15
| 2.8.2 | 6.8 | Market-wide Participant MHHS Supporting Functionality Ready | Suppliers, MOPs and DCs | The Code Bodies have confirmed on 15/09 that this activity has taken place | 2024 | 2025-09-22 | bar: 2025-01-01 to 2025-09-22
| 2.9 | 6.9 | Pre-M10 Service Activation |  |  | 2025-09-11 | 2025-09-18 |  | 2025-09-11: p; 2025-09-12: g; 2025-09-13: g; 2025-09-14: g; 2025-09-15: g; 2025-09-16: g; 2025-09-17: g; 2025-09-18: q
| 2.9.1 | 6.9.1 | Pre-M10 Service Activation - LDSOs | DIP Manager, Service Activation Team, LDSOs | There is a dependency on all LDSOs having completed this activity ahead of M10. There is a dependency on all LDSOs to have become MHHS qualified to enable this activity to be completed. | 2025-09-11 | 2025-09-18 |  | 2025-09-11: p; 2025-09-12: g; 2025-09-13: g; 2025-09-14: g; 2025-09-15: g; 2025-09-16: g; 2025-09-17: g; 2025-09-18: q
| 2.9.2 | 6.9.2 | Pre-M10 Service Activation - Suppliers and Agents | DIP Manager, Service Activation Team, Suppliers, Agents | There is a dependency on a minimum of one Supplier and their contracted Agents having completed this activity ahead of M10. There is a dependency on any Supplier or Agent going through this process to have become MHHS qualified to enable this activity to be completed. | 2025-09-11 | 2025-09-18 |  | 2025-09-11: p; 2025-09-12: g; 2025-09-13: g; 2025-09-14: g; 2025-09-15: g; 2025-09-16: g; 2025-09-17: g; 2025-09-18: q
Cutover Activities | 3.1 | 8.1 | Code Bodies |  |  | 2025-09-12 | 2025-09-22 |  | 2025-09-12: p; 2025-09-13: g; 2025-09-14: g; 2025-09-15: g; 2025-09-16: g; 2025-09-17: g; 2025-09-18: g; 2025-09-19: g; 2025-09-20: g; 2025-09-21: g; 2025-09-22: q
| 3.1.1 | 8.1.1 | Code Changes Designated (M8) | REC Code Manager, BSCCo, Ofgem, MHHS Programme | There is a dependency on the CCAG confirming the readiness of Code Bodies for M8 on 12/09/2025. | 2025-09-12 | 2025-09-22 |  | 2025-09-12: p; 2025-09-13: g; 2025-09-14: g; 2025-09-15: g; 2025-09-16: g; 2025-09-17: g; 2025-09-18: g; 2025-09-19: g; 2025-09-20: g; 2025-09-21: g; 2025-09-22: q
| 3.2 | 8.2 | Elexon Services |  |  | 2025-09-19 | 2025-09-22 |  | 2025-09-19: p; 2025-09-20: g; 2025-09-21: g; 2025-09-22: q
| 3.2.1 | 8.2.1 | Load Shaping Service (LSS) | Elexon and Elexon Service Providers |  | 2025-09-19 | 2025-09-22 |  | 2025-09-19: p; 2025-09-20: g; 2025-09-21: g; 2025-09-22: q
| 3.2.2 | 8.2.2 | Volume Allocation Service (VAS) | Elexon and Elexon Service Providers |  | 2025-09-19 | 2025-09-22 |  | 2025-09-19: p; 2025-09-20: g; 2025-09-21: g; 2025-09-22: q
| 3.2.3 | 8.2.3 | Market-wide Data Service (MDS) | Elexon and Elexon Service Providers |  | 2025-09-19 | 2025-09-22 |  | 2025-09-19: p; 2025-09-20: g; 2025-09-21: g; 2025-09-22: q
| 3.3 | 8.3 | Central Services Deployment of New Functionality |  |  | 2024-06-01 | 2025-09-22 | bar: 2025-01-01 to 2025-09-22
| 3.3.1 | 8.3.1 | DTS | Electralink, RECCo | As per standard DTS changes, RECCo will have provided ElectraLink with the relevant technical specification for the DTS release which will support M10. All Market Participants will be required to have implemented the changes to ensure continued operation of their Legacy processes. | 2025-09-19 | 2025-09-22 |  | 2025-09-19: p; 2025-09-20: g; 2025-09-21: g; 2025-09-22: q
| 3.3.2 | 8.3.2 | EES | RECCo | There is a dependency on the EES being onboarded to the DIP ahead of the M10 cutover weekend once the DIP portal is made available. | 2025-09-19 | 2025-09-22 |  | 2025-09-19: p; 2025-09-20: g; 2025-09-21: g; 2025-09-22: q
| 3.3.3 | 8.3.3 | DCC | DCC | This activity is dependent on the successful releases of the MHHS supporting versions of the CSS and DSP for M8 (CSS) and June 2024 (DSP). | 2024-06-01 | 2024-06-30
| 3.4 | 8.4 | LDSOs | LDSOs, St Clements | For MPRS to be deployed and able to communicate with the DIP, each LDSOs DCP will need to have become qualified so that the relevant LDSO can communicate with the DIP. There is also a dependency on all LDSOs being onboarded to the DIP ahead of the M10 Cutover weekend and following 05/09/2025 when the DIP portal is made available. | 2025-09-19 | 2025-09-22 |  | 2025-09-19: p; 2025-09-20: g; 2025-09-21: g; 2025-09-22: q
| 3.4.1 | 8.4.1 | MPRS – Registration Services, UMSO Role, LDSO Role |  |  | 2025-09-19 | 2025-09-22 |  | 2025-09-19: p; 2025-09-20: g; 2025-09-21: g; 2025-09-22: q
Post-M10 Cutover Activities | 4.1 | 9.1 | Pre-M11 Service Activation | DIP Manager, Service Activation Team, Suppliers, Agents |  | 2025-09-26 | 2025-10-22 |  | 2025-09-26: p; 2025-09-27: g; 2025-09-28: g; 2025-09-29: g; 2025-09-30: g; 2025-10-01: g; 2025-10-02: g; 2025-10-03: g; 2025-10-04: g; 2025-10-05: g; 2025-10-06: g; 2025-10-07: g; 2025-10-08: g; 2025-10-09: g; 2025-10-10: g; 2025-10-11: g; 2025-10-12: g; 2025-10-13: g; 2025-10-14: g; 2025-10-15: g; 2025-10-16: g; 2025-10-17: g; 2025-10-18: g; 2025-10-19: g; 2025-10-20: g; 2025-10-21: g; 2025-10-22: q
| 4.1.1 | 9.1.1 | Qualification Pathway 4 Service Activation |  | There is a dependency on any Supplier or Agent going through this process to have become MHHS qualified in Pathway 4 to enable this activity to be completed. | 2025-09-26 | 2025-10-03 |  | 2025-09-26: p; 2025-09-27: g; 2025-09-28: g; 2025-09-29: g; 2025-09-30: g; 2025-10-01: g; 2025-10-02: g; 2025-10-03: q
| 4.1.2 | 9.1.2 | Qualification Pathway 5 Service Activation |  | There is a dependency on any Supplier or Agent going through this process to have become MHHS qualified in Pathway 5 to enable this activity to be completed. | 2025-10-16 | 2025-10-22 |  | 2025-10-16: p; 2025-10-17: g; 2025-10-18: g; 2025-10-19: g; 2025-10-20: g; 2025-10-21: g; 2025-10-22: q
M10 Day 1 Choreography | 5.1 | 10 | IF-047 sent at 9am on Monday 22nd September by Elexon via the DIP to all LDSOs and EES | Elexon |  | 2025-09-22 | 2025-09-22 | bar: 2025-09-22
| 5.2 | 10 | All LDSOs and EES to load ISD files via the URL published within the IF-047 via the Elexon data store (note, this should contain the same ISD file as uploaded to the Elexon portal following 11th September, therefore it may not need to be applied by each party) | LDSOs, EES |  | 2025-09-22 | 2025-09-22 | bar: 2025-09-22
| 5.3 | 10 | Following successful loading of ISD data LDSOs can process New Connections via their DB01 interface to MPRS | LDSOs |  | 2025-09-22 | 2025-09-22 | bar: 2025-09-22
| 5.4 | 10 | Each LDSO will track successful sending of the IF-050 message to the DIP | LDSOs |  | 2025-09-22 | 2025-09-22 | bar: 2025-09-22
| 5.5 | 10 | EES will track successful receipt and processing of the IF-050 | EES |  | 2025-09-22 | 2025-09-22 | bar: 2025-09-22
M11 Day 1 Choreography | 6.1 | 11 | IF-047 sent at 9am on Monday 22nd October by Elexon via the DIP | Elexon |  | 2025-10-22 | 2025-10-22 | bar: 2025-10-22
Governance | 7.1 | 4 | TORWG | MHHS Programme |  | 2025-09-17 | 2025-09-17 | bar: 2025-09-17
| 7.2 | 4 | MCAG (Entry to M10) | MHHS Programme |  | 2025-09-19 | 2025-09-19 | bar: 2025-09-19
| 7.3 | 4 | Central Systems live (M10) | MHHS Programme |  | 2025-09-22 | 2025-09-22 | bar: 2025-09-22
| 7.4 | 4 | Codes designated at 00:00 (M8) | MHHS Programme |  | 2025-09-22 | 2025-09-22 | bar: 2025-09-22
| 7.5 | 4 | TORWG | MHHS Programme |  | 2025-09-23 | 2025-09-23 | bar: 2025-09-23
| 7.6 | 4 | PSG (M10 Acceptance Criteria validation) | MHHS Programme |  | 2025-09-24 | 2025-09-24 | bar: 2025-09-24
| 7.7 | 4 | TORWG | MHHS Programme |  | 2025-10-17 | 2025-10-17 | bar: 2025-10-17
| 7.8 | 4 | MCAG | MHHS Programme |  | 2025-10-20 | 2025-10-20 | bar: 2025-10-20
| 7.9 | 4 | PSG | MHHS Programme |  | 2025-10-22 | 2025-10-22 | bar: 2025-10-22
TORWG 17/09 Inputs | 8.1 | 4 | Confirmation from all LDSOs that DIP onboarding has taken place | LDSOs |  | 2025-08-22 | 2025-08-22 | bar: 2025-08-22
| 8.2 | 4 | Confirmation that all LDSOs have deployed MPRS 9 to production | LDSOs |  | 2025-09-01 | 2025-09-01 | bar: 2025-09-01
| 8.3 | 4 | Confirmation that population of Domestic Premises Indicator is complete | LDSOs, RECCo |  | 2025-09-08 | 2025-09-08 | bar: 2025-09-08
| 8.4 | 4 | Confirmation that Market Segment has been populated for 95% of LDSO portfolios | LDSOs |  | 2025-09-12 | 2025-09-12 | bar: 2025-09-12
| 8.5 | 4 | Confirmation of all pre-M10 parties | Code Bodies |  | 2025-09-15 | 2025-09-15 | bar: 2025-09-15
| 8.6 | 4 | Confirmation that all LDSOs have populated the ISD | LDSOs |  | 2025-09-15 | 2025-09-15 | bar: 2025-09-15
| 8.7 | 4 | Declaration from all Central Services and LDSOs that they are in a position to move forwards | DIP Manager, Elexon (ECS, ISD, Service Management), Electralink (DTS), RECCo (EES), DCC (CSS, DSP), LDSOs (MPRS, UMSO role, LDSO role) |  | 2025-09-15 | 2025-09-15 | bar: 2025-09-15
| 8.8 | 4 | Market-wide Participant MHHS Migration Supporting Functionality is ready to be deployed | Code Bodies |  | 2025-09-15 | 2025-09-15 | bar: 2025-09-15
MCAG 19/09 Inputs | 9.1 | 4 | Recommendation from TORWG that the Programme should enter M10 | TORWG Members, MHHS Transition Team |  | 2025-09-17 | 2025-09-17 | bar: 2025-09-17
| 9.2 | 4 | Production Service Activation Activities have taken place for all LDSOs, EES and Elexon Central Services | Service Activation Team |  | 2025-09-18 | 2025-09-18 | bar: 2025-09-18
TORWG 23/09 Inputs | 10.1 | 4 | Early Life Support model is in place | MHHS Programme |  | 2025-09-19 | 2025-09-19 | bar: 2025-09-19
| 10.2 | 4 | MCC Operational | MHHS Programme |  | 2025-09-19 | 2025-09-19 | bar: 2025-09-19
| 10.3 | 4 | Self-Declaration from all Central Services and LDSOs that Cutover activities have been successfully carried out | Electralink (DTS), RECCo (EES), DCC (CSS, DSP), LDSOs (MPRS, UMSO role, LDSO role) |  | 2025-09-22 | 2025-09-22 | bar: 2025-09-22
| 10.4 | 4 | Confirmation that DIP and ECS have been deployed, Service management is active, ISD has been populated | Elexon (ECS, ISD, Service Management), DIP Manager |  | 2025-09-22 | 2025-09-22 | bar: 2025-09-22
| 10.5 | 4 | Confirmation that Market Segment has been populated for 100% of LDSO portfolios | LDSOs |  | 2025-09-22 | 2025-09-22 | bar: 2025-09-22
| 10.6 | 4 | IF-047 message has been sent | Elexon |  | 2025-09-22 | 2025-09-22 | bar: 2025-09-22
| 10.7 | 4 | LDSOs have received the IF-047 message | LDSOs |  | 2025-09-22 | 2025-09-22 | bar: 2025-09-22
| 10.8 | 4 | EES has received the IF-047 message and loaded the ISD file | EES |  | 2025-09-22 | 2025-09-22 | bar: 2025-09-22
| 10.9 | 4 | Confirmation that the IF-050 has been sent and the number sent | LDSOs |  | 2025-09-22 | 2025-09-22 | bar: 2025-09-22
| 10.1 | 4 | Confirmation of the number of IF-050s | EES |  | 2025-09-22 | 2025-09-22 | bar: 2025-09-22
PSG 24/09 Inputs | 11 | 4 | Recommendation from TORWG that the M10 acceptance criteria have been met | TORWG Members, MHHS Transition Team, PSG |  | 2025-09-23 | 2025-09-23 | bar: 2025-09-23
TORWG 17/10 Inputs | 12.1 | 4 | Self-Declaration that MHHS Functionality will be deployed to Production by Qualified parties | All Qualified Parties |  | 2025-10-14 | 2025-10-14 | bar: 2025-10-14
| 12.2 | 4 | Qualification of all pre-M11 parties | Code Bodies |  | 2025-10-16 | 2025-10-16 | bar: 2025-10-16
| 12.3 | 4 | Self-Declaration that ISD file has been manually accessed and applied by all qualified Suppliers and Agents | All Qualified Parties |  | 2025-10-16 | 2025-10-16 | bar: 2025-10-16
MCAG 20/10 Inputs | 13 | 4 | Confirmation of Qualified Parties from TORWG and their readiness | TORWG, MHHS Transition Team |  | 2025-10-17 | 2025-10-17 | bar: 2025-10-17
PSG 22/10 Inputs | 14 | 4 | Recommendation from MCAG that the Programme can approve M11 / M12 | MCAG, MHHS Transition Team |  | 2025-10-20 | 2025-10-20 | bar: 2025-10-20
Note on H96: Following further clarity being provided by the DIP Manager, Suppliers and Agents qualified prior to M10 will have until 15th October 2025 to produce DIP certificates