**MHHS Participant Cutover Plan – Elexon**



|  |  |  |
| --- | --- | --- |
| Document Owner: | Document Number: | Version: |
| **Transition & Operational Readiness Team** | **MHHS-DEL3634** | **1.0** |
| Status: | Date: | **Classification:** |
| **Template issued to Participants** | **10/04/2025** | **Public** |

|  |  |  |
| --- | --- | --- |
| Document owner | Document number | Date |
|  |  |  |

# Contents

[1 Contents 2](#_Toc194919613)

[1.1 Change Record 3](#_Toc194919614)

[1.2 References 3](#_Toc194919615)

[1.3 Terminology 3](#_Toc194919616)

[1.4 Programme Milestones 4](#_Toc194919617)

[2 Introduction and Scope 5](#_Toc194919618)

[2.1 Introduction 5](#_Toc194919619)

[2.2 Scope 5](#_Toc194919620)

[3 Cutover Plan Requirements 6](#_Toc194919621)

[3.1 Key Requirements 6](#_Toc194919622)

[3.2 Activities set out within the M10 / M11 Cutover Plan 8](#_Toc194919623)

[4 Cutover Contact Details 9](#_Toc194919624)

## Change Record

|  |  |  |  |
| --- | --- | --- | --- |
| Date | Author | Version | Change Detail |
| 10/04/2025 | Transition & Operational Readiness Team | 1.0 | Template issued to Participants |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |

## References

|  |  |  |  |
| --- | --- | --- | --- |
| Document | Publisher | Published | Additional Information |
| MHHS-DEL2521 M10 / M11 Cutover Plan v1.1 | Transition & Operational Readiness Team | 01/04/2025 |  |
| MHHS-DEL2521 M10 / M11 Cutover Delivery Plan v1.1 | Transition & Operational Readiness Team | 01/04/2025 |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |

## Terminology

|  |  |
| --- | --- |
| Term | Description |
| BAU  | Business As Usual  |
| BSC | Balancing and Settlement Code |
| BSCCo | BSC Company |
| Central Service Providers | The providers that manage and operate the electricity Central Services, namely Elexon, DCC and ElectraLink.  |
| Central Services | The services that comprise the electricity central service delivery functions, namely the Elexon Central Services, Central Switching Service, Data Transfer Network and the central service delivery functions underpinning smart metering.  |
| Cutover Weekend | The period in which MHHS capabilities will be deployed by Central Services and LDSOs. Activities will occur on a Saturday and/or Sunday, enabling M10 milestone to be approved on the Wednesday |
| CSS | Central Switching Service |
| DCC | Data Communications Company |
| DCP | DIP Connection Provider |
| DIP | Data Integration Platform |
| DSP | Data Services Provider |
| ECS | Elexon Central Systems - MHHS Programme term used to describe the new MHHS Target Operating Model services being delivered under the Programme - Load Shaping, Market-wide Data, Volume Allocation and Industry Standing Data |
| EES | Electricity Enquiry Service |
| ELS | Early Life Support |
| ISD | Industry Standing Data |
| LDSO | Licensed Distribution System Operator |
| Legacy Arrangements | The existing arrangements set out under the BSC and REC.  |
| LSS | Load Shaping Service |
| MDS | Market-wide Data Service |
| MHHS | Market-wide Half-Hourly Settlement |
| MHHS Arrangements | The new MHHS arrangements as set out in the MHHS Core Design Artefacts. |
| MPAN | Meter Point Administration Number |
| MPRS | Metering Point Registration System |
| MSID | Metering System Identifier |
| MVC | Consists of the central systems and sufficient early adopters to enable the solution to go live. The early adopters have to consist of the right functional elements to allow the market to function - therefore will include the central systems, (i)DNOs, Suppliers and Service Providers. |
| REC | Retail Energy Code |
| RECCo | Retail Energy Code Company |
| Registration Service | The service operated by LDSOs |
| SIT | Systems Integration Testing |
| UMS | Unmetered Supplies |
| UMSO | Unmetered Supplies Operator |
| VAS | Volume Allocation Service |

## Programme Milestones

The below Programme milestones are referenced throughout this document.

M8 (Sep 2025) – Code Changes Delivered

M10 (Sep 2025) – Central Systems ready for migrating MPANs

M11 (Oct 2025) – Start of 18-month migration for Unmetered Supplies (UMS) / Advanced

M12 (Oct 2025) – Start of 18-month migration for Smart / Non-Smart

M13 (Sep 2025) – Load Shaping Service (LSS) Switched On

# Introduction and Scope

## Introduction

The M10 milestone is denoted as the point in time when Industry Central Services are ready to migrate MPANs, while M11 and M12 denote the point in time when Suppliers will be able to start initiating the migration of MPANs from the Legacy arrangements to the new MHHS arrangements. There are a number of activities that need to be carried out in order for the Central Services to be ready to migrate MPANs and for Industry Participants to start carrying out migrations. The M10/M11 Cutover Plan sets out the activities that MHHS Participants will be required to carry out in the lead up to M10, at M10, and between M10 and M11 to enable the Programme to successfully reach both M10 and M11 respectively.

These documents set out the request for Participants to develop their own participant Cutover Plans and highlights the minimum required set of information that is expected to be included within these plans. It outlines the key requirements that should be included and references the activities Participants are responsible for within the Programme M10/M11 Cutover Plan.

## Scope

The Scope of the Participant Cutover Plan is to outline the technical cutover activities that Programme Participants must undertake to ensure their systems are fully deployed, operational, and compliant with the M10/M11 Cutover Plan deadlines, enabling the Programme to successfully meet both the M10 and M11 milestones. In addition to outlining what these activities are, it also outlines the activities set out within the M10/M11 Cutover Plan which the Participant is responsible for.

The plan should:

* Detail specific system cutover activities, including technical deployments and data migrations required to support the delivery of new functionality in line with Programme deadlines
* Identify any dependencies on external parties for the delivery of your cutover activities
* Clearly reference the activities set out within this document – more guidance for which can be found below

Each Participant must create a tailored Cutover Plan incorporating these activities while ensuring it aligns with the overall Programme timelines.

This document does not prescribe detailed resourcing, risk mitigation strategies or internal governance processes for individual Participants. Each Participant is responsible for determining the required steps, risk management approaches and resources required to execute their Cutover Plan successfully.

# Cutover Plan Requirements

This section outlines the requirements that must be included within the Participant Cutover Plan.

In Section 3.1, the Programme has defined a minimum set of activities that they expect to see within participant cutover plans. This list is non-exhaustive and participant cutover plans should include the complete set of technical activity required to enable the participant to deploy their new functionality and operate within the MHHS arrangements. The requirements set out below at a minimum, must be included within your cutover plans.

In Section 3.2, this details the activities documented in the M10/M11 Cutover Plan that Participants are responsible for. Please ensure that all activities are explicitly referenced within the Plan so they can be easily cross-referenced.

## Key Requirements

|  |  |  |  |
| --- | --- | --- | --- |
| **Reference #** | **Requirement** | **Comments** | **Relevant Section of Plan** |
| 1 | **Please share your technical cutover plan for the DIP (including activities, timescales and responsible owners)***The deployment of the production release of the DIP environment. This should also reference the activities required to enable Participants to carry-out their webhook registration activities and request production certifications.* |  |  |
| 2 | **In reference to the activity above, please confirm that participants will be able to access the DIP Portal and to request Production Certificates in line with the dates in the Programme Cutover Plan. Please share when the process to enable this will be in place and operational***Participants will require this functionality no later than the dates set in the Programme Cutover Plan.* |  |  |
| 3 | **Please share your technical cutover plan for the LSS (including activities, timescales and responsible owners)***The deployment of the LSS to enable the market to operate under the MHHS arrangements.* |  |  |
| 4 | **Please share your technical cutover plan for the VAS (including activities, timescales and responsible owners)***The deployment of the VAS to enable the market to operate under the MHHS arrangements.* |  |  |
| 5 | **Please share your technical cutover plan for the MDS (including activities, timescales and responsible owners)***The deployment of the MDS to enable the market to operate under the MHHS arrangements.* |  |  |
| 6 | **Please share your technical cutover plan for the ISD (including activities, timescales and responsible owners)***The deployment of the ISD, ensuring the ISD data is reviewed before publication, and the ability for the service to generate an IF-047 and send to the DIP following the cutover weekend in line with the dates set out in the Programme Cutover Plan.* |  |  |
| 7 | **Please share your technical cutover plan to make the new Service Management arrangements operational (including activities, timescales and responsible owners)***Ensuring that consideration has been given to when the service management arrangements will be required in line with the deployment of new systems and functionality.* |  |  |
| 8 | **Please share your plan for enabling Participants to complete Service Activation (including activities, timescales and responsible owners)***The process for getting Participants service activated for Participants that qualify in the lead up to M10, and between M10 and M11.* |  |  |
| 9 | **Do you have any internal dependencies?** *Please list any internal dependencies between activities including internal governance.* |  |  |
| 10 | **Do you have any external dependencies?****Have these dependencies and the associated dates been agreed with the delivering party?***E.g., other parties implementing capabilities and external systems.* |  |  |
| 11 | **Please provide details of your Hypercare arrangements and when these will be in place***Hypercare arrangements to support the operation of the MHHS arrangements.* |  |  |
| 12 | **Please identify the key risks with the activities that you will be undertaking prior to and at the cutover along with the mitigation steps that you are taking** **Should any of these risks become issues, please set out the planned actions you would take to resolve these issues***I.e., if production deployments fail or are delayed (e.g. rollback/fix forward).* |  |  |

## Activities set out within the M10 / M11 Cutover Plan

**Please be aware that the dates outlined in the M10/M11 Cutover Plan are not *strictly* prescriptive.** These dates represent the final dates by which activities must be completed or where stated, the actual dates on which an activity must be completed. If you feel that any of these dates require change, please set out your rationale below.

**Please fill out the ‘Date activity is due to be completed by/on’ column, and where activities are due to take place earlier than the dates mentioned in the plan, please explain why this is the case.**

Note: some of the activities refer to declarations required by the Programme to enable governance decisions to be made to support M10 and M11 – please reference the relevant sections of the Programme M10/M11 Cutover Plan for more detail on these activities. Also, note that when a declaration is required on a specific day, this does not mean that the activity must be completed on that date. Instead, it indicates when the Programme needs to be informed that the activity has been completed.

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Cutover Plan Reference** | **Activity** | **Start Date** | **Due Date** |  **Date activity is due to be completed by/on** | **Commentary** |
| 5.5 | Early Life Support Implemented (Helix Hypercare arrangements) | N/A | 19/09/2025 |  |  |
| 7.2.1 | Production DIP Portal (DIP Deployment) | 05/09/2025 | 05/09/2025 |  |  |
| 7.2.1 | Production Certificates (DIP Deployment) | 05/09/2025 | 05/09/2025 |  |  |
| 4 | **Declaration:** Confirmation of Helix E2E Settlement Testing Complete **(17/09 TORWG input)** | 15/09/2025 | 15/09/2025 |  |  |
| 4 | **Declaration:** Declaration from all Central Services and LDSOs that they are in a position to move forwards **(17/09 TORWG input)** | 15/09/2025 | 15/09/2025 |  |  |
| 7.2.2 | Elexon Central Services Deployment | 19/09/2025 | 22/09/2025 |  |  |
| 7.2.3 | Service Management Go-Live | 19/09/2025 | 22/09/2025 |  |  |
| 4 | **Declaration:** Self-Declaration from all Central Services and LDSOs that Cutover activities have been successfully carried out **(23/09 TORWG input)** | 22/09/2025 | 22/09/2025 |  |  |
| 4 | **Declaration:** Confirmation that DIP and ECS have been deployed, Service management is active, ISD has been populated **(23/09 TORWG input)** | 22/09/2025 | 22/09/2025 |  |  |
| 4 | **Declaration:** IF-047 has been sent **(23/09 TORWG input)** | 22/09/2025 | 22/09/2025 |  |  |

# Cutover Contact Details

Please provide contact details for your Principal Contact and Deputy during the Cutover Period along with any other contacts that may be required to be contacted by the Programme to request information relating to your cutover activities.

(Phone Number and Email Address)