## Summary Sheet
Test Case Name | Test Case Description
TC_MI01 | To validate end-to-end coordination, escalation, and resolution of a Market Issue (MI).
Validate Elexon Service Desk logs MI, allocates a resolver, and monitors the resolution process.
Ensure correct routing of MI based on impacted party type (e.g., DIP, MP, Elexon).
TC_MI02 | LDSO identifies an issue processing settlement data that may impact market participants.
Elexon Service Desk is contacted by LDSO and coordinates issue resolution between LDSO and relevant parties.
TC_NI01 | Simulate or detect that a DIP message sent from a sender has not reached the recipient.
Elexon Service Desk validates issue, checks DIP logs, and notifies the receiving party.
Incident closed once delivery confirmation is received.
TC_NI03 | Data corruption identified by any party affects the validity or usability of the data.
Elexon Service Desk is contacted and initiates triage with all impacted parties and DIP support.
TC_NI04 | An incident involves ISD updates not notified. Downstream parties receive no indication.
Elexon Service Desk validates missing notifications and escalates for immediate fix.
TC_NI05 | Scheduled outage results in system unavailability, but parties are not pre-warned.
Elexon Service Desk logs, investigates lack of prior communication, and facilitates resolution.
TC_NI06 | DIP message is duplicated and received multiple times, potentially triggering errors.
Elexon Service Desk facilitates coordination and rectification steps.
TC_NI07 | One or more parties do not receive a required notification from DIP or other systems.
Elexon Service Desk logs and investigates, ensuring all parties are informed.
TC_PR01 | A Participant requests support for production environment issues via the Elexon Service Desk.
Elexon Service Desk assigns incident for investigation, logs updates, and tracks closure.
TC_SR01 | Elexon requests status updates from a Market Participant relating to a service request.
Elexon Service Desk records and manages updates provided by participants.
TC_PAR01 | The resolution of a Participant Access Request is delayed or incorrectly processed.
Elexon Service Desk ensures timely escalation and resolution tracking.
SITRETEST - SM10-TC01 | Validating the ability to escalate and resolve service failures through the Elexon Service Desk.
Elexon Service Desk contacts relevant parties and facilitates issue coordination and closure.
SITRETEST - SM07-TC02 | Confirm that Elexon Service Desk tracks and coordinates resolution of DIP system issues.
Elexon Service Desk identifies root cause and updates affected participants.
SITRESTEST - SM03-TC02 | Elexon Service Desk receives notification of a potential data mismatch and initiates engagement.
SITRESTEST - SM01-TC01 | Validate ability of Elexon Service Desk to handle and route multi-party incident.
Ensure communications are correctly logged and resolution process is followed.

## Overview Sheet
ID | Description | Objectives | Pre-conditions | Expected Results | Process
TC_MI01 | To validate end-to-end coordination, escalation, failover handling, and post-incident review across Market Participant and Elexon Service Desks during a simulated major incident. - Scenario DIP becomes unavailable or inaccessible for a large proportion of participants (e.g. >10% of the industry or multiple market roles affected | Incident Handling Between Parties | * ServiceNow, DIP Portal, and all relevant integrations are operational. * Elexon and Market Participant Service Desks are configured for incident sharing and synchronization. * Resolver Groups are pre-defined in all systems.. | Updates from Elexon and Market Participants reflect in real-time across Service Desks. | Major Incident Cross Party
TC_MI02 | LDSO identifies an issue processing settlement reports due to DUoS Billing system logic failures. | Incident Handling Between Parties | * DUoS Billing system is actively processing settlement reports. * LDSO and Elexon Service Desks are operational and integrated for major incident workflows. * MIM (Major Incident Management) processes are in place. | * LDSO correctly identifies and escalates the incident. * Elexon effectively coordinates major incident handling and resolution across multiple impacted parties. * Service desk updates and closure states are synchronized across all involved systems. * Incident resolution is clearly logged and audit-ready. | Major Incident Cross Party
TC_NI01 | Simulate or detect that a DIP message sent from REGS is not received by the Supplier within the expected timescale. | Incident Handling Between Parties | * REGS system is expected to send a DIP message. * DIP Portal and Market Participant Service Desks are operational. * Elexon's Service Desk is integrated via ServiceNow (or equivalent). | Updates from Elexon and Market Participants reflect in real-time across service desks. | Normal Incident Cross Party
TC_NI03 | Data corruption identified by any party affecting critical data exchanges | Incident Handling Between Parties | * Service Portal system is available for all parties. * DIP is operational but a corrupt message flow is identified. * Incident affects multiple parties (e.g., Supplier, LDSO, Data Service). * Escalation contacts available. * Incident meets criteria for CPSD escalation . | Incident is coordinated across all parties, resolved within agreed timelines, and fully documented in the system. | Major Incident Cross Party
TC_NI04 | An incident involves ISD updates not notified. Changes to ISD have been made but messages not received by multiple parties | Incident Handling Between Parties | * DIP Portal Operational * DIP Portal is available for Suppliers to verify ISD updates and message flows. * ServiceNow Functional * Suppliers and Elexon Service Desk can log, incidents. * Incident triage processes, resolver group responsibilities, and SLA thresholds are configured in ServiceNow. | * All parties receive timely and accurate broadcast messages via agreed channels. * ISD change failure is correctly triaged and escalated within SLAs. * DIP Portal usage and case logging are traceable in ServiceNow. * Resolution is clearly communicated and logged in ADO/ServiceNow with evidence. | Normal Incident Cross Party
TC_NI05 | Data Service identifies issue with Load Shaping data. Data Service identifies issues with the Load Shaping data during their estimation process | Incident Handling Between Parties | * DIP Portal and ServiceNow are available and accessible. * Data Service has access to raise and manage tickets with Elexon Service Desk. * Elexon triage process is active and relevant resolver groups are available. * Broadcast messaging mechanism is enabled (e.g., via ServiceNow or designated comms channel). * Historical/expected Load Shaping data is available for comparison during triage. | * Incident is accurately recorded and resolved through clear interaction between Data Service and Elexon. * Appropriate broadcast notification issued for visibility. * Issue resolution path (internal vs. external) clearly documented in ServiceNow. | Normal Incident Cross Party
TC_NI06 | LDSO unable to access the DIP. LDSO unable to access the DIP but the internal DIP adaptor is working | Incident Handling Between Parties | * LDSO internal DIP adaptor is operational and shows no local issues. * DIP Portal access is unavailable to LDSO (external-facing issue). * LDSO Service Desk has access to triage tools (including DIP Portal diagnostics). * LDSO and Elexon Service Desks are operational | * Incident is accurately triaged and logged by LDSO. * Elexon confirms outage and disseminates communication via broadcast channel. * Resolution is documented, and service restoration is clearly communicated to participants. | Normal Incident Cross Party
TC_NI07 | Incident Logging via ServiceNow Portal - DIP Registration Issue | Incident Logging via ServiceNow Portal | Relevant systems and integrations must be active (e.g. ServiceNow, DIP Portal). | * DIP Registration/User Privileges issues are correctly logged and categorized. * Resolution activities are tracked, communicated, and audited. * The Service User confirms resolution prior to closure. * Incident lifecycle is traceable and correctly managed in the system. | Normal Incident Cross Party
TC-PR01 | Problem Record Creation from Recurring Incidents | To validate that the ServiceNow platform can identify and escalate recurring incidents into a single Problem Record, allowing effective root cause analysis and long-term resolution. | * Relevant systems and integrations must be active (e.g., ServiceNow, DIP Portal). * Multiple incidents logged over time must have similar classification or symptoms. *Problem Management module in ServiceNow must be enabled and configured. | * ServiceNow identifies the recurring pattern and prompts Problem Record creation. * A single Problem Record is created and appropriately linked to all similar incidents. * Problem Record includes all relevant notes, assignments, and references. * Linked incidents are updated with the Problem Record ID and status. * Enables proactive and coordinated resolution planning. | Problem Management
TC-SR01 | Service Request Logging via ServiceNow | To verify that service requests can be successfully logged and tracked via the ServiceNow platform, with all requests routed through the Elexon Support Portal and assigned a default priority of P4. | * Relevant systems and integrations must be active (e.g., ServiceNow, DIP Portal). * The Elexon Support Portal (CSM Service Catalog) is available to Market Participants. * The service request type is preconfigured with routing and fulfillment workflows. | * The service request is successfully submitted via the Elexon Support Portal. * Request is assigned priority P4 and routed correctly. * The request is tracked to completion, including visibility of updates and final resolution. * Audit trail of request creation, ownership, and fulfillment is available | Service Request
TC_PAR01 | Testing of Parent/Child Accounts | Testing of ServiceNow Support Portal Access | * Parent and Child accounts are configured in ServiceNow with correct hierarchy. * Roles and access permissions are correctly set for both Parent and Child accounts. * Test users from both Parent and Child entities have portal access and case submission rights. * The ServiceNow instance is operational and integrated with relevant resolver workflows. * ServiceNow reporting/dashboards support account-bas | * Case is logged under the correct Child account and auto-linked to its Parent account. * Parent account user can view and track all Child account cases. * Service Desk triage acknowledges Parent/Child relationship and applies appropriate resolver group/escalation. * Closure updates are visible and accessible to both account levels via the portal. * Activity and case reporting reflect Parent/Child linkage in dashboards and reports. | Parent / Child Accounts
SITRETEST_SM10-TC01 | SU raises a request to amend an existing SLA | Validating the ability to escalate and resolve service failures through the Elexon Service Desk. |  | Elexon Service Desk contacts relevant parties and facilitates issue coordination and closure. | Amending Existing SLA
SITRETEST_SM07-TC02 | Search for an item not found request item to be added | Elexon Service Desk contacts relevant parties and facilitates issue coordination and closure. |  | Confirm that Elexon Service Desk tracks and coordinates resolution of DIP system issues. | Knowledge Management
SITRETEST_SM03-TC02 | Change requested - DCC Non Elexon Mngd | Validate ability of Elexon Service Desk to handle and route multi-party incident. |  | Change schedule available and confirmed as outside change window | Change Request
SITRETEST_SM01-TC01 | DIP service failure In Hours | Validate ability of Elexon Service Desk to handle and route multi-party incident. |  | Ensure communications are correctly logged and resolution process is followed. | Major Incident

## TC_MI01
Description | Objective | Preconditions | Test Steps Number | Test Steps | Expected Result | Involved Roles
To validate end-to-end coordination, escalation, failover handling, and post-incident review across Market Participant and Elexon Service Desks during a simulated major incident. - Scenario DIP becomes unavailable or inaccessible for a large proportion of participants (e.g. >10% of the industry or multiple market roles affected | Incident Handling Between Parties | ServiceNow, DIP Portal, and all relevant integrations are operational. Elexon and Market Participant Service Desks are configured for incident sharing and synchronization. Resolver groups are pre-defined in all systems.. | 1 | Log in to the Elexon Support Portal. | Updates from Elexon and Market Participants reflect in real-time across service desks. | Market Participants, Elexon Service Desk, Resolver Groups
|  |  | 2 | Create a new case using "Incident" category and provide a brief description simulating a high-impact outage: DIP becomes unavailable or inaccessible for a large proportion of participants (e.g. >10% of the industry or multiple market roles affected
|  |  | 3 | Submit incident and confirm receipt via email and ServiceNow notification.
|  |  | 4 | 1st Line Case Triage (within 15 minutes)
|  |  | 5 | Service Desk reviews the incident and classifies it as a potential "Major Incident Candidate."
|  |  | 6 | Validate that the case is not misrouted and correctly assigned to Incident Management.
|  |  | 7 | Elexon SME performs triage (section 5.8), evaluating business impact, urgency, and potential regulatory risk.
|  |  | 8 | Check for evidence of documented assessment (ServiceNow update, email).
|  |  | 9 | Confirm Major Incident Validity
|  |  | 10 | Review against thresholds in section 5.10 (e.g., multiple parties affected, system failure, settlement delays).
|  |  | 11 | Major Incident Manager reviews and confirms promotion to Major Incident.
|  |  | 12 | Promote incident to Major status in ServiceNow.
|  |  | 13 | Assign a Major Incident Manager and Triage Lead.
|  |  | 14 | Set status to “In Progress” and notify stakeholders via initial comms.
|  |  | 15 | Notify internal/external Resolver Groups based on impacted service (e.g., Settlement Services, DIP).
|  |  | 16 | Initiate a bridge call and circulate dial-in details to technical and business stakeholders.
|  |  | 17 | Ensure initial notification issued within 15 minutes.
|  |  | 18 | Verify updates are shared every 30–60 mins via portal and email, aligned with comms cadence table.
|  |  | 19 | Ensure technical updates and workaround actions are captured in ServiceNow.
|  |  | 20 | Validate real-time tracking and updates from all resolver groups.
|  |  | 21 | Confirm all systems restored and issue resolution notification to stakeholders.
|  |  | 22 | Transition incident to “Resolved” then “Closed” after stakeholder validation.
|  |  | 23 | Within 24 hours: schedule PIR meeting with key stakeholders.
|  |  | 24 | Produce PIR report capturing root cause, timeline, contributing factors, and corrective actions

## TC_MI02
Description | Objective | Preconditions | Test Steps Number | Test Steps | Expected Result | Involved Roles
LDSO identifies an issue processing settlement reports due to DUoS Billing system logic failures. | Incident Handling Between Parties | DUoS Billing system is actively processing settlement reports. LDSO and Elexon Service Desks are operational and integrated for major incident workflows. MIM (Major Incident Management) processes are in place. | 1 | LDSO identifies that DUoS settlement messages are failing due to billing system logic (e.g., invalid tariff format). | LDSO correctly identifies and escalates the incident. Elexon effectively coordinates major incident handling and resolution across multiple impacted parties. Service desk updates and closure states are synchronized across all involved systems. Incident resolution is clearly logged and audit-ready. | Market Participants, Elexon Service Desk, Resolver Groups
|  |  | 2 | LDSO triages and confirms the root cause internally.
|  |  | 3 | LDSO logs the incident internally and escalates to Elexon via the Support Portal.
|  |  | 4 | Elexon 1st Line Triage (within 15 mins)
|  |  | 5 | Validates the case, assigns it to Incident Management or flags as a Major Incident Candidate.
|  |  | 6 | Elexon SMEs review the issue, identify it affects multiple LDSOs using the shared billing logic, and recommend escalation.
|  |  | 7 | Major Incident Manager (MIM) is assigned, and severity is raised to Major Incident (P1).
|  |  | 8 | Initial communications are issued to the Major Incident Distribution List via ServiceNow and email.
|  |  | 9 | Teams call is established with all affected LDSOs and relevant Resolver Groups.
|  |  | 10 | LDSOs confirm the issue is a system design flaw and begin engaging their billing providers.
|  |  | 11 | The fix is implemented by LDSO vendors and verified through testing.
|  |  | 12 | Elexon validates resolution, updates the ServiceNow ticket, and marks the incident as Resolved then Closed.
|  |  | 13 | Audit logs, history, and communications are confirmed complete and retained.
|  |  | 14 | Post-Incident Review (PIR) is initiated within 24 hours.
|  |  | 15 | Issuing PIR documentation and recommendations.

## TC_NI01
Description | Objective | Preconditions | Test Steps Number | Test Steps | Expected Result | Involved Roles
Simulate or detect that a DIP message sent from REGS is not received by the Supplier within the expected timescale. | Incident Handling Between Parties | REGS system is expected to send a DIP message. DIP Portal and Market Participant Service Desks are operational. Elexon's Service Desk is integrated via ServiceNow (or equivalent). | 1 | Simulate that a DIP message from REGS is not received by the Supplier within the expected timeframe. | Updates from Elexon and Market Participants reflect in real-time across service desks. | Market Participants, Elexon Service Desk, Resolver Groups
|  |  | 2 | Supplier checks DIP Portal message status
|  |  | 3 | Supplier confirms no send activity recorded in DIP
|  |  | 4 | Supplier attempts internal resolution if message is queued
|  |  | 5 | Supplier escalates to LDSO with message ID, timestamp, and context
|  |  | 6 | LDSO confirms issue lies with REGS message generation and engages internal desk
|  |  | 7 | LDSO resolves issue and informs Supplier
|  |  | 8 | Supplier logs incident internally
|  |  | 9 | Supplier raises case with Elexon via Support Portal.
|  |  | 10 | Navigate to “Report a Service Issue” → Select Category: Participant Issues or DIP Communication Failure → Fill Subject and Description fields with DIP Message ID, expected send/receive time, and internal triage notes. (Ref: 5.4 & 5.5)
|  |  | 11 | Elexon Service Desk receives and performs 1st Line Triage.
|  |  | 12 | Within 15 minutes of case receipt, Desk verifies it is a valid Elexon-managed DIP issue and assigns to Incident Management. (Ref: 4.1, Steps 1–2)
|  |  | 13 | SME Triage starts
|  |  | 14 | Elexon SME assesses incident scope and impact (REGS, DIP, Supplier).
|  |  | 15 | SME triage records technical observations in the activity log. May engage LDSO if not previously contacted. (Ref: 4.1, Steps 6–7)
|  |  | 16 | Assign to correct Resolver Group (e.g., DIP Tech Resolvers, REGS backend).
|  |  | 17 | Incident reassigned to specific Resolver Group in ServiceNow. Status moves to In Progress. (Ref: 5.16)
|  |  | 18 | Supplier and Elexon monitor incident updates through respective Service Desks.Ensure real-time update visibility in both portals. Email notifications and portal views must match. (Ref: 5.13, ServiceNow Status Options)
|  |  | 19 | Resolution is implemented.
|  |  | 20 | Resolver applies fix or workaround. Notes added, and fix time recorded in ServiceNow.
|  |  | 21 | Elexon sends resolution comms.
|  |  | 22 | Portal auto-generates update email and closes ticket. Final comms should include root cause summary and resolution timestamp. (Ref: 5.21)
|  |  | 23 | Post-Incident Review (PIR) initiated by Elexon.
|  |  | 24 | PIR begins within 24 hours. Logs collected from all Resolver Groups and Market Participants. PIR recorded in ServiceNow as part of incident closure tasks. (Ref: 5.23)
|  |  | 25 | PIR actions and learnings recorded.
|  |  | 26 | Major learnings entered into Knowledge Management (section 11) or trigger Problem Record if issue is systemic. (Ref: 6.1–6.4)

## TC_NI03
Description | Objective | Preconditions | Test Steps Number | Test Steps | Expected Result | Involved Roles
Data corruption identified by any party affecting critical data exchanges | Incident Handling Between Parties | Service Portal system is available for all parties. DIP is operational but a corrupt message flow is identified. Incident affects multiple parties (e.g., Supplier, LDSO, Data Service). Escalation contacts available. Incident meets criteria for CPSD escalation . | 1 | Log in to the Elexon Support Portal with appropriate credentials. | Incident is coordinated across all parties, resolved within agreed timelines, and fully documented in the system. | Market Participants, Elexon Service Desk, Resolver Groups
|  |  | 2 | Create a new case under the “Incident” category describing a DIP outage affecting >10% of market participants.
|  |  | 3 | Submit the incident and confirm it is received via email and ServiceNow notification.
|  |  | 4 | Ensure 1st Line Support performs triage within 15 minutes and categorises the incident as a potential Major Incident.
|  |  | 5 | Verify the case is routed correctly and assigned to Incident Management.
|  |  | 6 | Elexon SME performs impact triage per section 5.8, assessing business disruption and regulatory risk.
|  |  | 7 | Check for evidence of SME assessment in ServiceNow and/or email.
|  |  | 8 | Review incident against Major Incident thresholds in section 5.10 (e.g., multiple parties, settlement delays, critical system failure).
|  |  | 9 | Major Incident Manager reviews and confirms whether to escalate to Major Incident.
|  |  | 10 | Promote the case to “Major Incident” in ServiceNow and assign a Major Incident Manager and Triage Lead.
|  |  | 11 | Set the incident status to “In Progress” and issue the first stakeholder communication.
|  |  | 12 | Notify relevant internal and external resolver groups (e.g., DIP, Settlement Services).
|  |  | 13 | Initiate a bridge call and distribute dial-in details to technical and business stakeholders.
|  |  | 14 | Confirm that the initial major incident notification is issued within 15 minutes of confirmation.
|  |  | 15 | Validate that update communications are shared every 30–60 minutes via portal/email.
|  |  | 16 | Capture all technical updates and workarounds in the ServiceNow incident record.
|  |  | 17 | Monitor real-time tracking and updates from all assigned resolver groups.
|  |  | 18 | Once resolved, confirm restoration of service and send final resolution notification to stakeholders.
|  |  | 19 | Transition the incident to “Resolved,” then “Closed” after confirmation from impacted stakeholders.
|  |  | 20 | Within 24 hours, schedule a Post-Incident Review (PIR) with key stakeholders.
|  |  | 21 | Produce and circulate the PIR report with root cause, impact timeline, contributing factors, and corrective actions.

## TC_NI04
Description | Objective | Preconditions | Test Steps Number | Test Steps | Expected Result | Involved Roles
An incident involves ISD updates not notified. Changes to ISD have been made but messages not received by multiple parties | Incident Handling Between Parties | DIP Portal Operational DIP Portal is available for Suppliers to verify ISD updates and message flows. ServiceNow Functional Suppliers and Elexon Service Desk can log, incidents. Incident triage processes, resolver group responsibilities, and SLA thresholds are configured in ServiceNow. | 1 | Supplier identifies missing ISD messages across multiple participants. Verifies using DIP Portal. Expected: Supplier confirms anomaly with broadcast message receipt. | All parties receive timely and accurate broadcast messages via agreed channels. ISD change failure is correctly triaged and escalated within SLAs. DIP Portal usage and case logging are traceable in ServiceNow. Resolution is clearly communicated and logged in ADO/ServiceNow with evidence. | Market Participants, Elexon Service Desk, Resolver Groups
|  |  | 2 | Supplier raises a case with Elexon Service Desk via ServiceNow. Expected: Incident is logged, triaged, and assigned a ticket ID.
|  |  | 3 | Elexon Service Desk conducts 1st Line triage within 15 minutes. Validates Elexon scope and assigns incident type. Expected: Ticket assigned correctly with triage notes added.
|  |  | 4 | 1st Line Triage performs validity check on ticket fields: category, subject, and description. Expected: Mandatory fields validated before progression.
|  |  | 5 | Elexon SME conducts technical triage. Assesses ISD data issues and cross-party impact. Expected: Priority set based on impact/urgency.
|  |  | 6 | SME determines if internal or external resolver support is needed. If external, dual triage is initiated. Expected: External stakeholders engaged where necessary.
|  |  | 7 | Engage resolver groups and product owner. Confirm technical ownership and priority. Expected: Collaboration initiated for impact analysis and solution planning.
|  |  | 8 | Service Desk confirms not a major incident. Engages resolver group. Expected: Technical triage continues under standard incident flow.
|  |  | 9 | Analyse and document root cause using logs and DIP data validation. Expected: Root cause logged and linked to ISD broadcast failure.
|  |  | 10 | Implement containment measures if impact is ongoing. Expected: Temporary mitigation actions applied while fix is developed.
|  |  | 11 | Resolver Group investigates ISD broadcast failure and implements technical fix. Expected: Root cause identified, remediation initiated.
|  |  | 12 | Elexon Service Desk issues a broadcast message to advise of the issue. Expected: Message received via agreed industry communication channels.
|  |  | 13 | Remediate the issue completely and confirm resolution through retesting. Expected: Broadcast flow validated as restored.
|  |  | 14 | Elexon confirms resolution and issues a follow-up broadcast message. Expected: Resolution confirmed and communicated to stakeholders.
|  |  | 15 | Supplier re-verifies via DIP Portal that ISD messages are being received. Expected: Messages flow correctly and are confirmed by supplier.
|  |  | 16 | Elexon logs final resolution, attaches evidence, and marks incident as resolved. Expected: Full audit trail and closure in ServiceNow/ADO.
|  |  | 17 | Initiate post-incident review and determine if a problem record is needed. Expected: Review outcome documented and linked to problem management if applicable.

## TC_NI05
Description | Objective | Preconditions | Test Steps Number | Test Steps | Expected Result | Involved Roles
Data Service identifies issue with Load Shaping data. Data Service identifies issues with the Load Shaping data during their estimation process | Incident Handling Between Parties | DIP Portal and ServiceNow are available and accessible. Data Service has access to raise and manage tickets with Elexon Service Desk. Elexon triage process is active and relevant resolver groups are available. Broadcast messaging mechanism is enabled (e.g., via ServiceNow or designated comms channel). Historical/expected Load Shaping data is available for comparison during triage. | 1 | Data Service identifies inconsistencies in Load Shaping data during estimation. Performs initial review using DIP Portal and historical Load Shaping trends. Expected: Anomaly in data confirmed by Data Service. | Incident is accurately recorded and resolved through clear interaction between Data Service and Elexon. Appropriate broadcast notification issued for visibility. Issue resolution path (internal vs. external) clearly documented in ServiceNow. | Market Participants, Elexon Service Desk, Resolver Groups
|  |  | 2 | Data Service raises a case in ServiceNow to the Elexon Service Desk with supporting evidence (e.g., data samples, logs). Expected: Incident logged and assigned a case ID.
|  |  | 3 | Elexon Service Desk 1st Line triage validates if the case is within scope and reassigns to incident management. Expected: Ticket correctly routed to incident workflow.
|  |  | 4 | Elexon SME triage compares Load Shaping data against expected/historical data sets and DIP records. Identifies errors in submitted data. Expected: Issue validated and flagged for correction by Data Service.
|  |  | 5 | If no error found by Elexon, Service Desk informs Data Service of triage outcome and closes the loop. Expected: Communication issued confirming no fault in central data.
|  |  | 6 | Data Service re-investigates based on Elexon feedback and discovers issue with internal estimation logic or input data. Resolves locally. Expected: Root cause isolated to internal systems and resolved.
|  |  | 7 | Elexon publishes a broadcast message to advise of the Load Shaping issue and resolution. Expected: Market participants notified via ServiceNow or agreed comms channel.
|  |  | 8 | Incident resolution and communication logged in ServiceNow, including evidence of investigation steps, internal vs. external fault path, and final resolution. Expected: End-to-end traceability of the incident.
|  |  | 9 | Post-incident, Data Service and Elexon optionally initiate review to confirm mitigation steps or improvements to estimation validation processes. Expected: Lessons learned shared if necessary.

## TC_NI06
Description | Objective | Preconditions | Test Steps Number | Test Steps | Expected Result | Involved Roles
LDSO unable to access the DIP. LDSO unable to access the DIP but the internal DIP adaptor is working | Incident Handling Between Parties | LDSO internal DIP adaptor is operational and shows no local issues. DIP Portal access is unavailable to LDSO (external-facing issue). LDSO Service Desk has access to triage tools (including DIP Portal diagnostics). LDSO and Elexon Service Desks are operational | 1 | LDSO observes that their internal DIP adaptor is operational, but they cannot access the external DIP Portal. They begin triage using internal tools and DIP Portal diagnostics. Expected: LDSO confirms issue is not local. | Incident is accurately triaged and logged by LDSO. Elexon confirms outage and disseminates communication via broadcast channel. Resolution is documented, and service restoration is clearly communicated to participants. | Market Participants, Elexon Service Desk, Resolver Groups
|  |  | 2 | LDSO Service Desk raises a case with Elexon Service Desk via ServiceNow including evidence (logs, error codes). Expected: Case is successfully logged and assigned for triage.
|  |  | 3 | Elexon Service Desk conducts 1st Line triage and escalates to SME triage to investigate potential DIP Portal outage. Expected: DIP access issue confirmed as a wider service disruption.
|  |  | 4 | Elexon initiates broadcast communication to advise of DIP Portal unavailability affecting one or more LDSOs. Expected: Market participants receive timely notice through agreed channels.
|  |  | 5 | Technical resolver groups apply fix (e.g., gateway reconfiguration, load balancer update, external auth issue resolved). Expected: DIP Portal access restored and validated.
|  |  | 6 | Elexon publishes a follow-up broadcast message confirming resolution. Expected: Stakeholders are informed of restoration and closure.
|  |  | 7 | ServiceNow entry is updated with full triage logs, evidence of resolution, and cross-reference to ADO ticket if used. Expected: End-to-end traceability captured in ITSM tooling.
|  |  | 8 | Post-incident review optionally initiated to assess cause of DIP Portal failure and opportunities for improved diagnostics or automated alerts. Expected: Lessons learned identified and shared if applicable.

## TC_NI07
Description | Objective | Preconditions | Test Step | Test Steps | Expected Result | Involved Roles
Incident Logging via ServiceNow Portal - DIP Registration Issue | Incident Logging via ServiceNow Portal | Relevant systems and integrations must be active (e.g. ServiceNow, DIP Portal). | 1 | A Service User with appropriate Data Role raises an incident in the ServiceNow portal for a DIP Registration or User Privileges issue. Expected: Issue is correctly described and logged under the appropriate category. | DIP Registration/User Privileges issues are correctly logged and categorized. Resolution activities are tracked, communicated, and audited. The Service User confirms resolution prior to closure. Incident lifecycle is traceable and correctly managed in the system. | Market Participants, Elexon Service Desk, Resolver Groups
|  |  | 2 | ServiceNow generates a unique incident ID, and the ticket appears in the incident queue for triage. Expected: Incident tracking begins with traceable reference.
|  |  | 3 | The incident undergoes 1st Line triage. The appropriate Service Management (SM) function is assigned, status set to 'New', and Priority P3 is applied. Expected: Ticket routed correctly with appropriate priority.
|  |  | 4 | Technical triage begins to assess the issue, using DIP Portal and account data to attempt resolution. Expected: Initial troubleshooting actions documented.
|  |  | 5 | The Technical Resolver and Product Owner are engaged for deeper investigation if no immediate fix is found. Expected: Issue escalated with clear handover.
|  |  | 6 | Communications are sent to the Service User confirming triage is ongoing or requesting additional information. Expected: User receives status updates and system notes are updated.
|  |  | 7 | The Resolver collaborates with the Service User to reproduce or validate the registration/privilege issue. Expected: Clear reproduction steps or user validation obtained.
|  |  | 8 | Technical Resolver identifies the issue (e.g., incorrect user role mapping, incomplete registration) and applies a fix. Expected: Resolution steps are documented in ServiceNow.
|  |  | 9 | A resolution update is sent to the Service User, and the incident status is updated to reflect resolution. Expected: Ticket marked as ‘Resolved’ with closure notes.
|  |  | 10 | The Service User reviews the applied fix and confirms the issue is resolved through ServiceNow. Expected: Confirmation recorded in the system.
|  |  | 11 | The Service User adds a final response and sets the incident status to ‘Closed’. Expected: Full incident lifecycle completed and traceable in ServiceNow.

## TC_PR01
Description | Objective | Preconditions | Test Step | Test Steps | Expected Result | Involved Roles
Problem Record Creation from Recurring Incidents | To validate that the ServiceNow platform can identify and escalate recurring incidents into a single Problem Record, allowing effective root cause analysis and long-term resolution. | Relevant systems and integrations must be active (e.g., ServiceNow, DIP Portal). Multiple incidents logged over time must have similar classification or symptoms. Problem Management module in ServiceNow must be enabled and configured. | 1 | Log three or more incidents in ServiceNow with similar or identical issue types (e.g., DIP message failure, user access error). Expected: ServiceNow pattern recognition engine detects similarities. | ServiceNow identifies the recurring pattern and prompts Problem Record creation. A single Problem Record is created and appropriately linked to all similar incidents. Problem Record includes all relevant notes, assignments, and references. Linked incidents are updated with the Problem Record ID and status. Enables proactive and coordinated resolution planning. | Elexon Service Desk, Resolver Groups
|  |  | 2 | Ensure these incidents share common configuration items (CIs), categories, symptoms, or descriptions. Expected: System recognizes correlation for grouping.
|  |  | 3 | ServiceNow flags a recurring pattern and suggests creation of a Problem Record. Expected: Prompt appears to initiate Problem Management workflow.
|  |  | 4 | Elexon Service Desk or Resolver Group reviews the suggested match and confirms Problem Record creation. Expected: Problem Record is generated and assigned a unique ID.
|  |  | 5 | Within the Problem Record, all related incidents are linked using the ‘Affected Incidents’ field or equivalent. Expected: Each incident is cross-referenced in the system.
|  |  | 6 | The Problem Record is assigned to the appropriate Resolver Group for root cause analysis. Expected: Ownership is established with accountability.
|  |  | 7 | Work notes and preliminary impact analysis are added to the Problem Record to inform investigation. Expected: Stakeholders are aligned on issue scope and potential impact.
|  |  | 8 | Notify Market Participants (if applicable) that a Problem Record is under investigation. Expected: Stakeholder awareness raised proactively.
|  |  | 9 | Verify that all linked incidents are updated with the Problem Record reference and inherit its status (e.g., under investigation). Expected: Full linkage confirmed in incident histories.
|  |  | 10 | Proceed with Root Cause Analysis under a separate test script or continuation workflow. Expected: Problem Management process progresses to resolution planning.

## TC_SR01
Description | Objective | Preconditions | Test Step | Test Steps | Expected Result | Involved Roles
Service Request Logging via ServiceNow | To verify that service requests can be successfully logged and tracked via the ServiceNow platform, with all requests routed through the Elexon Support Portal and assigned a default priority of P4. | Relevant systems and integrations must be active (e.g., ServiceNow, DIP Portal). The Elexon Support Portal (CSM Service Catalog) is available to Market Participants. The service request type is preconfigured with routing and fulfillment workflows. | 1 | Navigate to the Elexon Support Portal and open a new case. Expected: Access to the portal is successful and the case creation form is available. | The service request is successfully submitted via the Elexon Support Portal. Request is assigned priority P4 and routed correctly. The request is tracked to completion, including visibility of updates and final resolution. Audit trail of request creation, ownership, and fulfillment is available. | Market Participants, Elexon Service Desk, Resolver Groups
|  |  | 2 | Select an appropriate service request type such as Software Installation, Access Request, or Data Query. Expected: Predefined options are available and selectable based on request type.
|  |  | 3 | Complete all required fields in the form and submit the service request. Expected: Form validates inputs and accepts the submission.
|  |  | 4 | Confirm that the request is logged successfully and a unique Incident/Request ID is generated. Expected: Request appears in the portal dashboard.
|  |  | 5 | Verify that the request is automatically assigned a priority of P4 according to Elexon’s service request handling standards. Expected: Priority level is visible in the request details.
|  |  | 6 | Ensure that the request is routed to the correct resolver group based on the selected service type. Expected: Assignment group appears correctly in ServiceNow.
|  |  | 7 | Track the request through the portal dashboard, monitoring status changes and fulfillment progress. Expected: User can view real-time status updates.
|  |  | 8 | Optionally add comments or upload attachments to the service request and verify they are saved and displayed. Expected: All interactions are recorded in the request history.
|  |  | 9 | Verify request completion by receiving confirmation that the request has been fulfilled and closed. Expected: Resolution details and closure notification are visible to the user.

## TC_PAR01
Description | Objective | Preconditions | Test Step | Test Steps | Expected Result | Involved Roles
Testing of Parent/Child Accounts | Testing of ServiceNow Support Portal Access | Parent and Child accounts are configured in ServiceNow with correct hierarchy. Roles and access permissions are correctly set for both Parent and Child accounts. Test users from both Parent and Child entities have portal access and case submission rights. The ServiceNow instance is operational and integrated with relevant resolver workflows. ServiceNow reporting/dashboards support account-based filtering and visibility. | 1 | Log an incident using credentials of a Child Account (e.g. Supplier or Participant). Ensure the incident is correctly recorded under the Child entity and auto-linked to the configured Parent (e.g. Hosting Company or MSP). Expected: Incident routing aligns with account hierarchy; ServiceNow reflects parent-child association. | Case is logged under the correct Child account and auto-linked to its Parent account. Parent account user can view and track all Child account cases. Service Desk triage acknowledges Parent/Child relationship and applies appropriate resolver group/escalation. Closure updates are visible and accessible to both account levels via the portal. Activity and case reporting reflect Parent/Child linkage in dashboards and reports. | Child Account User (e.g. Supplier/Participant) Parent Account User (e.g. Holding Company or MSP) Elexon Service Desk Resolver Groups (if escalation needed)
|  |  | 2 | Login as a Parent Account user and verify visibility of the Child Account’s submitted case via the ServiceNow portal. Expected: Parent can see and track all linked child cases; only associated cases are shown.
|  |  | 3 | Confirm that other Child accounts (not under the same parent) cannot view each other’s cases, maintaining strict account isolation. Expected: Visibility boundaries enforced across Participants.
|  |  | 4 | ServiceNow enforces correct access rights: Participants logging on behalf of Clients can view those cases but cannot access cases submitted directly by other Hosting Clients. Expected: Role-based visibility works per participant access policies.
|  |  | 5 | Elexon Service Desk triages the incident, recognizing the parent/child linkage. Ensure resolver groups and SLAs are applied based on the Parent account's configuration. Expected: Escalation flows honor the hierarchy and respond with aligned SLAs.
|  |  | 6 | Resolve the case and confirm that closure updates are issued to both the Parent and Child users. Expected: Closure communication reaches all relevant parties via portal and email.
|  |  | 7 | Access ServiceNow dashboards to review audit trails, activity logs, and case summaries. Validate that reports reflect the parent-child relationship for filtering and reporting. Expected: Data views and KPIs are segmented and roll up as designed.
|  |  | 8 | Submit a second case from a different Hosting Client (outside the tested Parent) and verify the Participant cannot see this case. Expected: Case visibility aligns with configured client isolation model.
|  |  | 9 | Simulate a Participant logging a case with Elexon on behalf of a Managed Services Client. Ensure the Participant can track this case and the Managed Client sees their case details. Expected: Dual visibility allowed only where acting-on-behalf is configured.

## SITRETEST - SM10-TC01
No. |  | Test Case Id |  |  |  | Test Case Title
TC01 |  | SIT_OPS_SM10_TC01 |  |  |  | SU raises a request to amend an existing SLA
Test Case Title | Key Journey Events | Step No. | Business Process | Traceability Requirement | Service Producing Trigger | Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
SU raises a request to amend an existing SLA | Raise Case | 1 |  | LLSD v1.1 section 15 | Service User |  | Service User raises a case in the SM portal (CSM Service Catalog - Elexon Support) by selecting the 'Report a Service Issue' option and completing the following fields In the Requested by field - [Raisers name] In the Organisation name / Party ID - [Enter Org Name or Party ID] or select the I do not have a party ID In the Market Participant ID [Enter Party ID] or select I do not have a party ID From the Category drop box - select the Category (Mandatory) - Refer to Ops manual Subject - Request to amend Service Level Description - Amendment to Service Level URL or related page section - insert if required Click submit Refer to Ops manual for Response and resolution SLA, category dropdown options | Case Reference Displayed | Y
|  | 2 |  |  | Service Management |  | The request is reviewed by Service Management and assessed as a change of Service Level requirement and assign to Service Design/Commercial team | Change of Service level identified and ticket assigned to correct team with a status of in progress | Y
| Assess Case | 3 |  |  | Service Design / Commercial |  | Case is assessed and identified Service Level requirement, agreed sign off and service activation | SLA identified, change signed off and change activated | Y
| Activate | 4 |  |  | Service Design / Commercial |  | Service Activation completes with required tables/DBs being updated | Change is activated and reflected in correct tables/DBs Business process catalogue Service Catalogue Application Catalogue | Y
|  | 5 |  |  | Service Design / Commercial |  | Maintain Service Level Management Framework | Service Level Mngt Framework updated | Y
| Outcome communicated | 6 |  |  | Service Desk |  | Communication to requestor advising of the outcome | Outcome received by the requestor, change of SLA made | Y

## SITRETEST - SM07-TC02
No. |  | Test Case Id |  |  |  | Test Case Title
TC02 |  | SIT_OPS_SM07_TC02 |  |  |  | Search for an item not found request item to be added
Test Case Title | Key Journey Events | Step No. | Business Process | Traceability Requirement | Service Producing Trigger | Input/Trigger | Service Recipient Processor of Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
KM Item search fails, Request to Create an item | Services User searches for KM item | 1 |  | LLSD v1.1 Section 16 | Service User |  |  | Service Users accesses the Service Management Portal [Insert link] | Welcome to Elexon Support screen is displayed | Y
|  | 2 |  |  | Service User |  |  | Service user clicks the Glossary option from the tool bar | Glossary page is displayed | Y
|  | 3 |  |  | Service User |  |  | Service user selects the corresponding letter to search for an item e.g. D for DIP related KM - | Knowledge items returned against selected criteria | Y
|  | 4 |  |  | Service User |  |  | Service user identifies required item and reviews to ensure answers their query unable to locate Tips and best practices for effectively using DIP | Service user cannot find the item which answers their query, this needs to be created and raised via the Service Desk. | Y
| Request to create KM item | 5 |  |  | Service User |  |  | Service User raises a case in the SM portal (CSM Service Catalog - Elexon Support) by selecting the 'Report a Service Issue' option and completing the following fields In the Requested by field - [Raisers name] In the Organisation name / Party ID - [Enter Org Name or Party ID] or select the I do not have a party ID In the Market Participant ID [Enter Party ID] or select I do not have a party ID From the Category drop box - select the Category (Mandatory) - Select the appropriate category Subject - Add item to Glossary Description - No documentation for searched topic - Tips and best practices for effectively using DIP URL or related page section - insert if required Click submit Refer to Operations manual for category drop downs | Service User completes request to add item to Glossary. | Y
|  | 6 |  |  | Service Desk |  |  | Case is retrieves from the queue and triaged identifying the correct team to assign the case to | Case is triaged and assigned to Knowledge Author | Y
|  | 7 |  |  | Knowledge Author |  |  | Reviews the case to identify the requirement | Requirements identified | Y
|  | 8 |  |  | Knowledge Author |  |  | Creates the Knowledge item | Assigns to the Knowledge reviewer | N
|  | 9 |  |  | Knowledge Reviewer |  |  | Review the knowledge item | Assigns to the Knowledge Manager | N
|  | 10 |  |  | Knowledge Manager |  |  | Reviews and approves and publishes the KM item | Item now available in KM using Glossary search | Y
|  | 11 |  |  | Service User |  |  | Confirms item now available | Test End. | Y

## SITRESTEST - SM03-TC02
No. |  | Test Case Id |  |  |  | Test Case Title
TC02 |  | MHHS-DEL3196 SITOPS SM03 TC02 |  |  |  | Change requested - DCC Non Elexon Mngd
Test Case Title | Key Journey Events | Step No. | Business Process | Traceability Requirement | Service Producing Trigger | Service Recipient Processor of Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
Change requested - DCC system |  | 1 |  | LLSD v1.1 Section 10 | DCC |  | DCC request a change to a DCC managed system outside of the agreed change window | Change schedule available and confirmed as outside change window | Y
|  | 2 |  |  | TBC |  | Process tbc - Refer to Operations manual for engagement and comms methods |  | Y

## SITRESTEST - SM01-TC01
No. |  | Test Case Id |  |  |  | Test Case Title
TC01 |  | SIT_OPS_SM01_TC01 |  |  |  | DIP service failure In Hours
Test Case Title | Key Journey Events | Step No. | Business Process | Traceability Requirement | Service Producing Trigger | Input/Trigger | Test Step | Key Validation & Test Evidence | Evidence Required
DIP service failure in hours | Raise case | 1 |  | SDD v2.4 section 6 LLSD v1.1 Section 7 | SDS |  | Note: This case needs to be raised for DIP Service failure in hours Service User SDS raises a case in the SM portal (CSM Service Catalog - Elexon Support) by selecting the 'Report a Service Issue' option and completing the following fields In the Requested by field - [Raisers name] In the Organisation name / Party ID - [Enter Org Name or Party ID] or select the I do not have a party ID In the Market Participant ID [Enter Party ID] or select I do not have a party ID From the Category drop box - select the Category (Mandatory) - Select the appropriate category Subject - SDS receiving http error message Description - SDS receiving http error message URL or related page section - insert if required Click submit Refer to Operations manual for Category drop down options DIP SP raise the case directly into Service Now Refer to Operations manual for Category drop down options | Case Reference displayed | Y
|  | 2 |  |  | Elexon Service Desk |  | Elexon Service Desk retrieve the case from the queue . The case undergoes review and 1st line triage to identify the correct SM function for the case to be assigned to Ticket status is set to New | Case is triaged within 15 mins Case is assessed as a Major Incident candidate and assigned to the Major Incident Manager | Y
| Prmote to MI | 3 |  |  | Major Incident Manager |  | Incident promotion request is reviewed by the Major Incident Manager performing validity checks as to whether a Major Incident by Major Incident Manager on a case by case basis Refer to operations manual for details on validity checks | Incident assessed as valid Major Incident | Y
|  | 4 |  |  | Major Incident Manager |  | Incident ticket promoted to Major Incident Severity = S1 Priority = P1 Status = In progress Refer to Operations manual for status options | Incident ticket updated correctly | Y
| Initial Comms | 5 |  |  | Major Incident Manager |  | Initial comms are sent via email to the MI Comms team list Note: The comms list recipients is tbc and will be a standard list os recipients The commination list for Major Incidents will be agreed at a later date and available in Service Now | Validate recipients receive the MI communication | Y
|  | 6 |  |  | Major Incident Manager |  | Major Incident Manager engages the MI team (Technical Resolver teams, product owner) and establishes MI bridge Comms for the engagement comms method - refer to Operations manual Note: Ticket assigned to Tech Resolver group (MIM remains accountable) | DIP Tech Resolver team/s, Product Mngr acknowledge and accept the issue | Y
|  | 7 |  |  | Service Desk |  | Incident update Communication issued to Service Users via ticket updates on the portal and email notification from Service now each time ticket is updated) Refer to Operations Manual for comms frequency and details | Incident updates received by Service Users | Y
| Circular required | 8 |  |  | Product Owner |  | Assess whether Industry Circular required Note: If Industry impacting then Circular sent - details to be provided in the Operations manual | Industry Circular is required | Y
|  | 9 |  |  | Major Incident Manager |  | BSC website is updated with Industry Circular details Refer to Ops Manual for details on where in BSC website the circular details will be located | BSC website is updated correctly | Y
| Investigate | 10 |  |  | Major Incident Manager / DIP Technical Resolvers |  | MI Investigation starts DIP Technical Resolver team review the issue and confirm sufficient information supplied to progress Incident ticket status remains at In progress | Correct teams engaged - DIP SP | Y
|  | 11 |  |  | Major Incident Manager / DIP Technical Resolvers |  | Restorative actions identified, no Change required - Incident ticket status updated with fix details Mandatory Fields to be updated - tbc refer to operations manual Ticket status remains at In progress | Fix identified that does not require a Change to be raised for implementation, ticket is updated | Y
|  | 13 |  |  | DIP Tech Resolver Group / Major Incident Manager |  | Implement restorative actions | Actions to rectify the incident have been completed successfully | Y
| Resolve | 14 |  |  | DIP Tech Resolver Group / Major Incident Manager |  | Issue is deemed as being resolved, ticket is updated to reflect status of resolved and any other updates | Incident ticket reflects resolved | Y
|  | 15 |  |  | Product Owner |  | Assess whether Industry Circular required If Industry impacting then Circular sent - refer to Operations manual for further detail | Industry Circular is required and issued | Y
|  | 16 |  |  | Major Incident Manager |  | BSC website is update with Industry Circular details Refer to Ops Manual for details - where in BSC website will be located | BSC website is updated correctly | Y
| Comms | 17 |  |  | Service Desk |  | Communication sent to Service Users notifying them the incident is resolved (via ticket updates on portal, and email notification Service now) | Service user reviews actions taken, ticket status | Y
| Report | 18 |  |  | Service Desk / MIM / DIP Technical Resolvers |  | Post incident review takes place and Major Incident report produced and attached to ticket in Service Now within 3 WDs Refer to Operations Manual for further details | MI Report completed and attached to Incident ticket | Y
| Close | 19 |  |  | Service User (participant) |  | Service Users verify the issue is resolved and closes the incident ticket, (ticket will be closed in 5 days automatically) | Incident is set to closed | Y